Education Technology Plan

July 1, 2011 - June 30, 2016

"In times of drastic change, it is the learners who inherit the future.

The learned usually find themselves beautifully equipped

to live in a world that no longer exists."
—Eric Hoffer

District Tech Plan Creation Date: October 9, 2010

| County Name: | Butte |
| --- | --- |
| District Name: | Biggs Unified School District |
| County and District Code: | 04- 61408 |
| Superintendent’s Name: | Bill Cornelius |
| Address: | 300 B Street |
| City & Zip Code: | Biggs 95917 |
| Phone Number & Ext.: | (530) 868-1281 |
| FAX#: | (530) 868-1615 |
| Tech Plan Contact: | Dave Niemeyer |
| Job Title: | Technology Coordinator |
| Email: | dniemeye@biggs.org |
| Back up Contact Name: | Pam Ragan |
| Job Title: | Financial Officer |
| Email: | pragan@biggs.org |

Acknowledgments

School Board of Trustees

Kathryn Sheppard, President

Vickie Speegle, Vice President

Kari L. Wheeler, Clerk

Kris Scott

Mike Felkins

District Educational Technology Plan Team

District Personnel

Curriculum / Data Personnel

Char Locey, Biggs Elementary School (Contact for BUSD/BCOE Data Committee)

April Robinson, Biggs High School (Contact for BUSD/BCOE Data Committee)

Tim Sheridan

Vera Bridges

Technology Personnel

Dave Niemeyer, Technology Coordinator

Financial Personnel

Pam Ragan, Financial Officer

Site Administrators

Bill Cornelius, Superintendent and Biggs High School Principal

Stacy Doughman, Principal, Biggs Elementary and Richvale Elementary

Teachers

Char Locey

Scott Gates

Parents / Students

Jake Rogers, Technology Student Assistant

Government Agencies

CTAP Region 2, Ed Tech Coordinator – Nancy Silva

Community Group & Businesses

Computers for Classrooms

Table of Contents

District Profile	1

Section 1: Tech Plan Vision & Duration	3

Section 2: Stakeholders	3

Section 3: Curriculum & Data Driven Technology Goals	4

Section 4: Professional Development	17

Section 5: Infrastructure, Hardware, Software, & Technical Support	25

Section 6: Education Technology Funding & Budget	32

Section 7: Monitoring & Evaluation of Technology Plan	35

Section 8: Adult Literacy and Technology	36

Section 9: Effective, Research-Based Strategies	37

Appendix C – Criteria for EETT Technology Plans	48

# District Profile

The city of Biggs, with a population of approximately 1,805, is situated in Butte County, California.  The town lies 60 miles north of Sacramento.  The school district encompasses 135 square miles, which includes the communities of Biggs and Richvale and is in the heart of a rich agricultural area. California State University, Chico and Butte and Yuba Colleges provide students with easy access to post-graduate educational opportunities.

Biggs USD has a 2010-11 enrollment of 579 students. Approximately 20% of the student population are English language learners with the majority having Spanish as their primary language.  Approximately 70% of the students qualify for free or reduced lunch district-wide.  The district’s schools include:  Biggs Elementary School (K-5), Biggs Middle School (6-8), Biggs High School (9-12), a community day schools, all in the town of Biggs; and Richvale Elementary (K-5) School located in the neighboring community of Richvale.

The district employs a Superintendent/High School Principal and a K-8 Principal, 36 NCLB Highly Qualified Teachers and 49 classified, confidential and non-teaching personnel.

The educational program uses current state-adopted and district-approved instructional materials. Students have opportunities to participate in a career technical education, after school programs, sports, extra curricular activities and student leadership activities, which broaden their educational experience.

Student support services include:  special education classes, resource specialist programs, a speech and language program, counseling and psychologist services.  The district receives state and federal categorical program funds that include:  Gifted and Talented Education (GATE), School and Library Improvement Program (SLIP), Economic Impact Aid (EIA), Safe and Drug Free Schools (S&DATE) and Title I, II, III, IV and V funding.

| Biggs Unified School District School Data, 2010 |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Number of Schools | Total Enrollment | # Full-Time Equivalent Teachers | Pupil-Teacher Ratio |
| Elementary | 2 | 274 | 14.5 | 18.8 |
| Middle | 1 | 96 | 3 | 32 |
| High School | 1 | 199 | 13 | 15.3 |
| Continuation | 1 | 10 | 1 | 10 |
| Total | 5 | 569 | 31.5 | 18 |

|  | District |
| --- | --- |
| American Indian | .2 % |
| Asian | .5 % |
| Pacific Islander | .2 % |
| Filipino | 0 % |
| Hispanic | 40.1 % |
| African American | 0 % |
| White | 58.4 % |
| Multiple/No Response | .5 % |
| Total | 100 % |

|  | District |
| --- | --- |
| English Learners % | 27.7 % |
| Students with Disabilities % | 12.9 % |
| Graduates (prior year) | 42 |
| UC/CSU Eligible Grads (prior year) | 14 |
| % Fully Credentialed Teachers | 100 % |
| % of total population receiving Free or Reduced Price Meals | 69.6 % |

| Biggs Unified District State Accountability: Academic Performance Index (API) |  |  |  |
| --- | --- | --- | --- |
| 2009 API Base | 2010 Growth API | 2009-10 Growth | Met 2010 API Criteria |
| 689 | 687 | -2 | Yes |
| Biggs Unified District Federal Accountability: Adequate Yearly Progress (AYP) |  |  |  |
| Made AYP 2009-10: No Met 13 of 22 AYP Criteria |  |  |  |

|  | Met AYP Criteria English-Language Arts | Met AYP Criteria Mathematics |
| --- | --- | --- |
| Percent Proficient | No | No |
| Participation Rate | Yes | Yes |
| API - Additional Indicator for AYP | Yes, see above for API |  |
| Graduation Rate | 100% |  |
| PI Status | Not in PI |  |

BUSD 2010 STAR TEST RESULTS

# Section 1: Tech Plan Vision & Duration

This revised EdTech Plan encompasses the next five years, from July 1, 2011 – June 30, 2016. It is the result of discussion and collaboration among a diverse representation of administrators, teachers, parents, students, and business partners. Our technology committee began reviewing our former research-based 2006-2011 Education Technology Plan in the spring of 2010. We assessed our achievements to date, discussed lessons learned, determined our new district vision for the next five years, and developed strategies to get us there. Our revised tech plan envisions a 21st century teaching and learning environment grounded in the reality of our knowledge-based Digital Age. Used as a tool, not an end in itself, technology will be an integral part of the way we work, teach, and learn. Students will use technology seamlessly, as an integral part of the learning process to enhance their critical thinking, problem solving skills, and communication skills. Educators will learn to use technology to create teachable moments, not just wait for them and to provide just-in-time learning interventions. District staff will use technology to facilitate effective and efficient organizational operations and decision-making within the district. Interactive communication and activities among home, school, and community will increase and improve student learning.

# Section 2: Stakeholders

Our ongoing technology planning is guided by a collaborative vision of how technology can help students meet grade level academic content standards and reach the desired learning outcomes identified by our school district and its community. Annually in the fall, our Education Technology Advisory Committee reviews the district’s curriculum goals and current student achievement data and then determines how technology may be used effectively and efficiently to help students reach the academic goals for the year. Our committee is comprised of district and site representatives who are responsible for implementing the plan, including district curriculum, data, and information technology staff; site administrators, teachers, students, and parents as well as partners in higher education, community non-profit groups, and local businesses. The CTAP representative on our tech plan team offered technical assistance with: the data analyses and revision of our goals and objectives; professional development planning and implementation; EETT Formula Funding; E-rate; K12 Vouchers; compliance issues; hardware, software, and infrastructure.  In addition to our committee meetings, our district website and e-mail provides stakeholders with a mechanism for ongoing updates and input regarding the objectives, funding, budgets, and curricular guidelines contained within our technology plan.

Our District continues to solicit, expand, and sustain our partnerships with stakeholders to enhance the integration of educational technology into the curriculum. Our district recognizes that schools alone do not have the resources or expertise to keep pace with rapidly changing technology. We believe that these partnerships will help us serve the growing needs of an increasingly technical and global education system and society.

The Biggs Unified School District also has a District English Language Acquisition Committee (DELAC) which meets regularly throughout the year.

# Section 3: Curriculum & Data Driven Technology Goals

3a. Current Technology Access

According to current district records, our student to computer ratio for computers four years old or newer is 9:1  (569 students in the district with 63 four-year-old or newer computers.) All teachers at all  BUSD schools in our district have access to a minimum of one multi-media computer with internet access in their classrooms as well as in the Library/Media Centers, and/ or Computer Labs, before, during, and after school hours.

The following charts outline the technology access available in classrooms, library/media centers, or labs for all students, including special education, GATE, English Language Learners, both during and after school hours. Access to appropriate site-based technology resources has been evaluated through district and site inventory records and summarized below.

| Biggs Elementary School |  |
| --- | --- |
| Enrollment (Unofficial CBEDS 2010) | 240 |
| Total # of Computers for Instructional Use | 74 |
| Total # of Computers in Classrooms | 29 |
| Total # of Internet Connected Computers in Classrooms | 29 |
| Total # of Computers in Classrooms older than 48 months | 29 |
| Total # of Computers in Classrooms 48 months old or newer | 0 |
| Student to Computer Ratio – Computers 48 months old or newer only | 30:1 |
| Total # of Computers in Computer Labs | 42 |
| Total # of Computers in Computer Labs older than 48 months | 34 |
| Total # of Computers in Computer Labs 48 months old or newer only | 8 |
| Total # of Computers in Library/Media Center | 3 |
| Internet Access Connection Speed (DSL, T-1, >T-1) | T-1 |
| Before & After School Student Access to Computers – Days & Time | M – Th, 3-4 pm |

| Richvale Elementary School |  |
| --- | --- |
| Enrollment (Unofficial CBEDS 2010) | 34 |
| Total # of Computers for Instructional Use | 31 |
| Total # of Computers in Classrooms | 4 |
| Total # of Internet Connected Computers in Classrooms | 4 |
| Total # of Computers in Classrooms older than 48 months | 4 |
| Total # of Computers in Classrooms 48 months old or newer | 0 |
| Student to Computer Ratio – Computers 48 months old or newer only | 3.4:1 |
| Total # of Computers in Computer Labs | 26 |
| Total # of Computers in Computer Labs older than 48 months | 16 |
| Total # of Computers in Computer Labs 48 months old or newer only | 10 |
| Total # of Computers in Library/Media Center | 1 |
| Internet Access Connection Speed (DSL, T-1, >T-1) | T-1 |
| Before & After School Student Access to Computers – Days & Time | M – Th, 3-4 pm |

| Biggs Middle School |  |
| --- | --- |
| Enrollment (Unofficial CBEDS 2010) | 96 |
| Total # of Computers for Instructional Use | 40 |
| Total # of Computers in Classrooms | 9 |
| Total # of Internet Connected Computers in Classrooms | 9 |
| Total # of Computers in Classrooms older than 48 months | 4 |
| Total # of Computers in Classrooms 48 months old or newer | 5 |
| Student to Computer Ratio – Computers 48 months old or newer only | 19.2 : 1 |
| Total # of Computers in Computer Labs | 31 |
| Total # of Computers in Computer Labs older than 48 months | 31 |
| Total # of Computers in Computer Labs 48 months old or newer only | 0 |
| Total # of Computers in Library/Media Center | 0 |
| Internet Access Connection Speed (DSL, T-1, >T-1) | T-1 |
| Before & After School Student Access to Computers – Days & Time | M – Th, 3-4 pm |
| Biggs High School |  |
| Enrollment (Unofficial CBEDS 2010) | 189 |
| Total # of Computers for Instructional Use | 73 |
| Total # of Computers in Classrooms | 26 |
| Total # of Internet Connected Computers in Classrooms | 26 |
| Total # of Computers in Classrooms older than 48 months | 21 |
| Total # of Computers in Classrooms 48 months old or newer | 5 |
| Student to Computer Ratio – Computers 48 months old or newer only | 4.8 : 1 |
| Total # of Computers in Computer Labs | 34 |
| Total # of Computers in Computer Labs older than 48 months | 0 |
| Total # of Computers in Computer Labs 48 months old or newer only | 34 |
| Total # of Computers in Library/Media Center | 13 |
| Internet Access Connection Speed (DSL, T-1, >T-1) | T-1 |
| Before & After School Student Access to Computers – Days & Time | M – Th, 3:30-4:30 pm |

| Biggs Continuation School (Secondary) |  |
| --- | --- |
| Enrollment (Unofficial CBEDS 2010) | 10 |
| Total # of Computers for Instructional Use | 5 |
| Total # of Computers in Classrooms | 5 |
| Total # of Internet Connected Computers in Classrooms | 5 |
| Total # of Computers in Classrooms older than 48 months | 4 |
| Total # of Computers in Classrooms 48 months old or newer | 1 |
| Student to Computer Ratio – Computers 48 months old or newer only | 10 : 1 |
| Internet Access Connection Speed (DSL, T-1, >T-1) | T-1 |
| Before & After School Student Access to Computers – Days & Time | None |

3b. Current Technology Integration in Curriculum

The following data offers a snapshot of the technology skills integrated in our district curriculum by subject area and typical frequency of use by grade level bands.

| Focus / Subject Area | Typical Uses of Technology | Typical Frequency |
| --- | --- | --- |
| English / Language Arts | K-3: Read Naturally, Study Island, Renaissance Place, Starfall.com., (computers, monitors, keyboards, mice used at all levels) 4-6: Read Naturally, Study Island, Renaissance Place, Mavis Beacon, Word, 7-8 Word, PowerPoint, Internet, Publisher, DVD, test generator, and web site licensing purchased along with the English textbooks, keyboarding, video projector 9-12: Word, Keyboarding English Learners: Read Naturally, Study Island, Renaissance Place Special Education: Read Naturally, Study Island, Renaissance Place | K-3: 4 days a week 4-6:4 days a week 7-8: 3-4 times/week 9-12: Daily English Learners: Daily Special Education: Every day |
| Mathematics | K-3: Study Island, Math Blaster, Cool Math 4-6: Study Island, Math Blaster 7-8: DVD, test generator, and web site licensing purchased along with the mathematics textbooks 9-12: Mathblaster, Class Zone English Learners: Study Island, Math Blaster Special Education: Study Island, Math Blaster | K-3:4 days a week 4-6: 4 days a week 7-8:Daily 9-12: Daily English Learners: Daily Special Education: Every day |
| Science | 4-6: Power Point 7-8: Learn360, Internet resources, DVD’s and CD’s for pictures, DVD, test generator, and web site licensing purchased along with the science textbooks, digital camera 9-12: Learn360, digital cameras English Learners: Word for reports, Special Education: Learn360, Internet resources, DVD’s and CD’s for pictures | 4-6: Once per trimester 7-8: Twice weekly 9-12: Daily English Learners: Special Education: Daily |
| Social Science / History | 4-6: Power Point, Video Projector 7-8: Internet sites for research, DVD, test generator, and web site licensing purchased along with the social science textbooks, digital camera 9-12: Internet resources for research of current events, digital camera English Learners: Internet sites for research Special Education: Internet sites for research. | 4-6: Once per trimester 7-8: Daily 9-12: weekly English Learners: Weekly Special Education: Weekly |
| Library | K-3: Follett/Destiny, book scanners 4-6: Follett/Destiny, Reading Counts, Reading Inventory 7-8: Reading Counts, Reading Inventory 9-12: Reading Counts, Reading Inventory, scanner, English Learners: Reading Counts, Reading Inventory Special Education: Reading Counts, Reading Inventory | K-3: Daily 4-6: Daily 7-8: twice quarterly 9-12: twice quarterly English Learners: twice quarterly Special Education: twice quarterly |

In addition to the typical uses of technology described above, educators at all grade levels use our student information system (SIS) Aeries daily for attendance. In addition, approximately 50% of teachers use Aeries as their electronic gradebook. Our district-wide electronic learning assessment system, Datadirector, is used by 75 % of all teachers in the school district (22% report that they use it currently, 53% have used it at least once).  It has not been used by 25% of all teachers.  Much work must be done here.

3c. Summary of District’s Curricular Planning Documents

Biggs Unified School District has established clear curricular goals tied to the academic content standards monitored by various district and site-based assessment systems, and referenced in comprehensive district planning documents and efforts. The common underpinning of all our district and school improvement plans is to improve student achievement of the state content standards as specified in the BIGGS UNIFIED SCHOOL DISTRICT LEA PLAN

Biggs Unified School District Curricular Goals

Our school board adopts key district goals annually, which are tied to and support the adopted, state approved, content standards in all academic areas and support the LEA plan. Each of our schools aligns its site-based curricular goals directly to the district’s LEA Plan and school board’s key goals in their annually updated site-based comprehensive single plans for student achievement.

Based on our student data, federal and state mandates, and research-based best practices, our district’s current key curricular goals are:

- All schools in the district will meet or exceed the NCLB Annual Measurable Objectives (AMO’s) for student proficiency, including all ethnic/racial, socio-economically disadvantaged and students with disabilities subgroups with the state content standards in English / Language Arts and Math. By June 30, 2014, all students in the district will be proficient or better with English/Language Arts and Math grade level content standards.

- The district will meet all of its AYP criteria annually including requirements for numerically significant subgroups.

- All schools in the district will meet or exceed the state’s Annual Performance Index (API) growth target as well as the API growth targets for each numerically significant ethnic/racial, socio-economically disadvantaged and students with disabilities subgroups at the school.

- The district will work with site administration to collect and analyze school and student data and develop continuous cycles and plans for school improvement including: improving curriculum, improving instruction, improving student support & intervention, improving the monitoring of student achievement, and improving home/ school/ and community partnerships.

- All students will be educated in learning environments that are safe, drug-free, and conducive to learning.

These district goals and corresponding specific measurable objectives that support them can be found in the following district and site comprehensive planning documents.

  - California academic content standards and frameworks.

  - District curriculum guides aligned with CA academic content standards.

  - District evaluation criteria for textbook adoption.

  - District student and teacher technology standards.

  - District LEA Plan

  - The district plan for English Learners (EL) describes the policies for identifying, assessing, and reporting students who have a primary language other than English. This EL Master Plan provides details on the reclassification procedure and the English Language Development and instructional programs to be provided to EL students to assist them in meeting and/or exceeding state academic content standards and graduation requirements.

  - The Policy and Procedures handbooks for each program which details the philosophy and goals, and policy and procedures regarding students, instruction, promotion and retention, equity, administration, personnel, community relations, business, and much more.

  - Site–based Single Plan for Student Achievement, SARC, WASC and CCR self-study reviews and actions plans.

  - The District’s current Educational Technology Plan.

3d- 3k Curricular Driven Technology Goals, Implementation Plans, Benchmarks, Timelines, Monitoring and Evaluation

All of the Curriculum Component Criteria 3d-3k elements are included in the curricular driven action plan charts in the Section 3: Action Plan pages that follow. Our curricular driven technology plans include clear, specific, realistic goals and measurable objectives that will support our district’s curriculum goals and student achievement of the state content standards.

The following goals will strategically meet our students’ need to acquire and refine their 21st century information and communication technology skills in order to improve the effectiveness, efficiency, and ideally, the enjoyment of their learning experiences as they master the core content standards.

Here is a summary of our curricular driven Education Technology goals.

Goal 1: Improve Student Achievement & Close Student Achievement Gaps

Teachers will integrate technology in the district’s curriculum to support the district curricular goal of ALL students attaining proficiency or better with ELA & math grade level content standards by end of the 2013-14 school year and maintain every year thereafter.

Goal 2: Student Acquisition of Technology and Information Literacy Skills.

ALL Students will acquire the National Education Technology grade level profile standards for students (NETS) to support achievement of the academic standards in the classroom, district curricular goals, and ultimately for lifelong learning and success in our digital society.

Goal 3: Student Acquisition of Digital Citizenship Skills

All students will be proficient with grade level ethical use of technology and internet safety skills (NETS for students: Digital Citizenship- standard #5).

Goal 4: Improve Student Data Collection, Analysis & Decision Making

District teachers and administrators will use technology to improve the collection, analysis, reporting, and use of formative, benchmark, and state student achievement data.

Goal 5: Improve Communication Among Home, School, and Community

District teachers and administrators will use technology to improve communication among home, school, and community.

Goals, objectives, benchmarks, implementation strategies, and timelines can be found in the pages that follow.

#### Biggs Unified School District Technology Action Plan

#### July 1, 2011– June 30, 2016 
(Appendix C Sections: 3d-3k)

Section 3d

Goal 1: Improve Student Achievement & Close Student Achievement Gaps

Teachers will integrate technology in the district’s curriculum to support the district curricular goal of ALL students attaining proficiency or better with ELA & math grade level content standards by end of the 2013-14 school year and maintain 100% proficiency annually.

Target Group:  All students including special education, English Learners, and GATE students.

Goal 1: Specific Measurable Objective by June 2016

Objective 1:      By June 2014, 100% of all district students will be proficient or better with state grade level standards in math and English Language Arts supported by state and district approved instructional resources, technology-based supplemental resources, professional development, student achievement data-driven decision making, and collaboration time (Professional Learning Community).*(~ NCLB AMO benchmark for all students including significant  subgroups by 2014)

Goal 1: Annual Benchmarks for Objective 1

Year 1: minimum of 60% by June 2012	Year 3: minimum of  100% by June 2014

Year 2: minimum of 75% by June 2013	Year 4: minimum of 100% by June 2015

Year 5:  maintain a minimum of 100% by June 2016

Goal 1: Evaluation Instrument(s) & Data

Instruments: Trimester /Quarterly Grade level assessments; Annual STAR/CST test results in English/Language Arts; CAHSEE

Data: Percentage scoring proficient or above/ passing

Instrument: Grade/subject level district and site professional development and collaboration meeting times / agendas / participation records and outcomes.

Data: % of teachers participating: Calibrated and articulated standards-aligned Grade/subject level objectives and assessments across the district and standardized list of District supported research based programs and practices.

Instrument: Ongoing Classroom Observations by site admin./ principal aligned to teachers’ evaluation schedule

Data: Teachers’ use of standards-aligned learning objectives, instructional and intervention time, research based programs, practices, and arrangements.

Instrument: Annual Site Academic Software Survey:

Data: Curriculum-based state and district approved software and productivity software in use at each site.

Instrument: Annual CDE EdTech Profile online tech proficiency survey ( www.edtechprofile.org )

Data: teacher’s self assessed technology and integration skills

Data reviewers

District Technology Coordinator, Technology Committee, site administrators and Media Center/ Library staff will analyze end of school year results annually between June and September and report to stakeholders annually in October.

Goal 1: Enhancing Student Achievement with Technology
Implementation Strategies / Timelines

- Beginning in the 2011-12 school year and continuing through the duration of the tech plan,, the LEA will coordinate quarterly grade and / or subject area district professional learning community meetings to develop and refine the district’s common viable articulated ELA and math curriculum comprised of common essential grade level content standards, relevant information & communication technology skills and aligned assessments.

- Annually, the district and the school(s) will invest the necessary time to identify and/ or review grade level essential standards and assessments based on CDE’s latest CST Blueprints and released test questions.

- Annually, purchase as needed state adopted instructional materials (K-8 ), standards-aligned textbooks (9-12) and supplemental curriculum-based technology resources (adopted and/ or CLRN approved) and ensure they  are being used with fidelity  in the classroom during monthly classroom visits by school administration.

- Ongoing, the district, principal, and teachers will research, learn, and integrate research-based best practices and technology that support specific ELA and Math student achievement needs identified during data reviews of significant subgroup populations at the school.

- Annually, the district and the school(s) will effectively allocate funding, time, training and human resources to overcome the school’s identified barriers to student academic achievement.

- Annually, support site-based selective class size reduction in key curricular areas identified as needing attention.

- Annually, increase learning time in key curricular areas identified as needing attention.

- During the 2011-12 school year, develop reading and math intervention programs for students in grades 5 to 8, inclusive, whose reading scores are Far below Basic and Below Basic in the CST performance level. The tiered immediate intervention program will be implemented by fall 2011.

- Annually, provide direct instruction in reading at grade level.

- Every school year, assess students periodically throughout the year with common grade level standards-aligned assessments to monitor student progress and provide immediate intervention support.

- Annually, provide students with adequate learning support including, but not limited to, a standards-aligned curriculum, quality instructional materials, technology access and resources, support services, and supplies for every pupil.

- Annually, provide professional development on adopted curriculum and technology resources (such as SB 472 (formerly AB 466) for teachers, AB 430 (formerly AB 75) training for site admins.)

- Beginning in fall 2011 and every year thereafter, provide systematic professional development and learning community collaboration time for site administration and teachers to align standards-based instruction and quarterly assessments horizontally and vertically through grade levels in the district, review data, learn and share best practices including the use of technology.

- By fall 2011, design and distribute an annual site academic software usage survey.

- By fall 2011, create and distribute a matrix of CLRN approved E/LA curriculum and intervention software that is supported by the district.

- Beginning in the fall 2011 and annually thereafter, provide professional development on district/ CLRN approved curriculum software and online resources as needed.

- Annually, continue to leverage grant, district, school, site council, and community resources to increase access to technology resources, hardware, and peripherals for students and teachers.

- Annually, continue to provide technology productivity and integration training as needed.

- Ongoing district support and professional development opportunities on the integration of E/LA skills and standards across the curriculum including career tech courses.

Goal 1: Digital Resources to be Integrated

- Adopted Text Supplemental Tech resources including publisher software and websites.

- CLRN and district approved curriculum software such as: Renaissance Learning,  Accelerated Reader, Accelerated and Star Math, AutoCAD, Reading Counts, Adobe Master Suite (including Dreamweaver, Photoshop, Illustrator, Flash, Acrobat), United Streaming, Math Blaster, Earobics, Mavis Beacon, Read Naturally, Eureka Career Software.

- Diagnostic reading, writing, and math proficiency software.

- Microsoft Office and other productivity software.

- Internet Access and Resources

- Peripherals such as LCD projectors, digital cameras, video cameras, scanners, and printers.

- Online Professional Development and Learning Communities

Section 3e

Goal 2: Student Acquisition of Technology and Information Literacy Skills

ALL students will be proficient or better with the National Education Technology (NETS) grade level profile standards for students or a county office equivalent to support achievement of the academic standards in the classroom, district curricular goals, and ultimately for lifelong learning and success in our digital society.

Target Group:  All students including special education, English Learner, and GATE students.

Goal 2: Specific Measurable Objective by June 2016

Objective 1: By June 2016, 100% of students in grades K-12 students in grades will be proficient or better with grade level NETS standards (or district equivalent).

Students will learn the NETS skills during relevant curricular assignments and develop a portfolio of NETS integrated assignments during the year.

- Creativity and Innovation

- Communication & Collaboration

- Research and Information Fluency – (information literacy)

- Critical Thinking, Problem Solving, and Decision-making

- Digital Citizenship –(includes social, ethical, copyright, and cyber safety issues).

- Technology Operations and Concepts

Goal 2: Annual Benchmarks for Objective 1

Year 1: minimum of 60% by June 2012	Year 3: minimum of 80% by June 2014

Year 2: minimum of 70% by June 2013	Year 4: minimum of 90% by June 2015

Year 5:  minimum of 100% by June 2016

Goal 2: Evaluation Instrument(s) & Data

Instrument: End of year portfolio of NETS integrated assignments

Data: Percentage achieving grade level NETS standards

Instrument: Annual CDE Ed Tech Profile (www.edtechprofile.org )

Data: Teachers’ self assessed technology integration proficiency skills.

Data reviewers

District Technology Coordinator, site administrators and Media Center/ Library staff will analyze end of school year results annually between June and September and report to stakeholders annually in October.

Goal 2: Student Acquisition of Technology & Information Literacy Skills
Implementation Strategies / Timelines

- During the 2011-12 school year, a focus group of teachers, librarians, and media assistants, in the district will research NETS resources and design scaffolded K-12 NETS curriculum.

- Beginning in the summer/fall 2011 and annually thereafter, provide Professional Development opportunities (from the District, and CTAP Region 2) to K-12 teachers on integrating the student NETS grade level skills and standards in their curriculum. Provide incentives for PD completion.

- By fall 2012, Students will begin systematically learning the NETS skills including technology productivity tools and information literacy, as appropriate, during curricular assignments.

- By spring 2013, begin administering annually the standards-aligned grade span NETS based exit assessments / portfolios for grades K-12.

Goal 2: Digital Resources to be Integrated

- Adopted Text Supplemental Tech resources including publisher software and websites.

- CLRN and district approved curriculum software such as: Renaissance Learning and PLATO products,  Accelerated Reader, Jostens Learning, Reading Counts, Kerswell, MovieMaker, FrontPage, Dreamweaver,  Freedom web publishing software, United Streaming

- A variety of grading programs such as GradeQuick and Grade Machine, Web-based student assessment platform such as Edusoft and web based student information and reporting platforms such as Aeries..

- Microsoft Office and other productivity software.

- No Cost / Low Cost - Internet Resources

- Peripherals such as LCD projectors, interactive white boards, digital cameras, video cameras, printers, and document cameras (ELMO).

Sections 3f & 3G

Goal 3: Ethical Use of Technology (Copyright) and Internet Safety)

All students will be proficient or better with grade level ethical use of technology and internet safety standards (NETS #5- Digital Citizenship).
Target Group: All students including special education, English Learner, and GATE students.

Goal 3: Specific Measurable Objective by June 2016

Objective 1: By June 2016, 100% of students in grades K-12 will be proficient or better with grade level NETS standard # 5- Digital Citizenship –(includes social, ethical, copyright, and cyber safety issues).

Goal 3: Annual Benchmarks for Objective 1

Year 1: minimum of  60% by June 2012	Year 3: minimum of  80% by June 2014

Year 2: minimum of  70% by June 2013	Year 4: minimum of  90% by June 2015

Year 5:  minimum of  100%  by June 2016

Goal 3: Evaluation Instrument(s) & Data

Instrument: Lesson plans integrating ethical use of technology including copyright and plagiarism

Data: % of teachers participating in the integration of lesson plans on ethical use of technology including copyright and plagiarism.

Instrument: Lesson plans integrating technology on internet safety and cyber-bullying.

Data: % of teachers participating in the integration of lesson plans on internet safety and cyber-bullying.

Instrument Rubric for Grade level student portfolio, presentations, and/or classroom work which will demonstrate technical skills and information literacy. Annual High school graduation computer competency assessment.

Data: Percentage meeting grade-level NET standards

Instrument: Annual Ed Tech Profile Survey

Data: teachers’ and students’ self assessed technology and integration skills

Data reviewers

District Technology Coordinator, eTAG, site administrators and Media Center/ Library staff will analyze end of school year results annually between June and September and report to stakeholders annually in October.

Goal 3: Ethical Use of Technology (Copyright) and Internet Safety
Implementation Strategies / Timelines

## During the 2011-2012 school year, district teachers will develop a scaffolded, articulated K- 8th grade and 9-12th grade NETs technology integration curriculum aligned to NETS standard # 5: Digital Citizenship. Curriculum results will be reviewed annually in June and modified as necessary.

## During the 2011-2012 school year, all teachers will be offered professional development opportunities on the Ethical Use of Technology and Internet Safety for students aligned to the NETS student standard # 5: Digital Citizenship, offered through CTAP Region 2 or the equivalent.

## Beginning in the fall 2012 and then annually thereafter, all K-12th grade students will begin systematically learning grade level NETS standard # 5: Digital Citizenship skills during curricular assignments.

## Beginning in the spring 2013, grade-level technology assessments and/or portfolio reviews will be conducted at the end of each school year.

## By fall 2011, roll-out a revised acceptable use policy for students addressing internet safety, cyberbullying, and plagiarism.

Goal 3: Digital Resources to be Integrated

  - Adopted Text Supplemental Tech resources including publisher software and websites.

  - CLRN and district approved curriculum software and/ or free Digital Citizenship internet resources

  - Microsoft Office Professional Suite and other productivity software.

  - Peripherals such as LCD projectors, interactive white boards, digital cameras, video cameras, printers, and document cameras (ELMO).

Section 3h

District Policy on Equitable Access

It is district policy to provide ALL students and teachers with equal access to all of the school’s technology to support achievement of the academic standards in the classroom, district curricular goals, and ultimately for success in the workplace. Student subgroups will have access to the same NETS integration activities and high standards expected of all other students, although the programs and methods for achieving the objectives may be adapted to best meet individual student needs. Students with an active Individualized Education Program (IEP) have appropriate access to technology hardware, peripherals, and software including assistive technology as deemed appropriate and defined by the IEP site team and the students’ IEP goals. EL students have appropriate access to technology hardware, peripherals, and software needed to support their English language acquisition as well as their achievement of the academic standards.

#### Section 3i

#### Goal 4: Efficient & Effective Student Data Collection, Analysis & Decision Making

District administrators and teachers will use technology to improve the collection, analysis, reporting, and use of formative, benchmark, and state student achievement data.

Target Group: All district schools.

Goal 4: Specific Measurable Objectives by June 2016

Objective 1: By June 2016, 100% of teachers will use the district’s full suite of SIS/ABI and electronic learning assessment tools to analyze student data and make data-driven decisions to meet individual student academic needs.

Goal 4: Annual Benchmarks for Objective 1

Year 1: minimum of 60% by June 2012	Year 3: minimum of 80% by June 2014

Year 2: minimum of 70% by June 2013	Year 4: minimum of  90% by June 2015

Year 5:  minimum of 100% by June 2016

Goal 4: Evaluation Instrument(s) & Data

Instrument:  electronic learning assessment tools

Data: % of teachers using electronic learning assessment tools to inform instruction.

Instrument: SIS usage records

Data: % of teachers using all SIS suite components

Instruments: District SIS suite training participation records

Data: % of teachers completing training – all components

Data reviewers

District Technology Coordinator, site administrators and Media Center/ Library staff will analyze end of school year results annually between June and September and report to stakeholders annually in October.

Goal 4: Efficient & Effective Student Data Collection, Analysis & Decision Making

Implementation Strategies / Timelines

Use of Technology

- During the 2011 - 2012 school year and every year thereafter until we meet our June 2016 objective, we will continue the rollout of Aeries integrated student assessment components.

- During the 2011 – 2012 school year and every year thereafter as needed, participating teachers will get necessary training in using multi-data profile analysis reports in Aeries Browser Interface (ABI).

- Annually, provide systematic professional development and collaboration time for administration and teachers to improve student achievement assessment, data collection, analysis, reporting, and data driven decision-making.

Goal 4: Digital Resources to be Integrated

- SIS program the district is currently using: Aeries

- Diagnostic reading, writing, and math digital applications

- Web-based student learning diagnostic assessment platform such as DataDirector.

- Online assessment data sites e.g. CDE’s Dataquest

- Excel Spreadsheets

#### Section 3j

#### Goal 5: Improve Communication Among Home, School, and Community

Districts administrators and teachers will use technology to improve communication among home, school, and community.

Target Group: Admins., teachers, key clerical staff, parents, and the community.

Goal 5: Specific Measurable Objective by June 2016

Objective 1: By June 2016, 100% administrators and teachers will have pertinent, timely, up-to-date district and classroom information posted on school and / or district web sites.

Annual Benchmarks for Objective 1

Year 1: minimum of 60% by June 2012	Year 3: minimum of 80% by June 2014

Year 2: minimum of 70% by June 2013	Year 4: minimum of 90% by June 2015

Year 5:  minimum of 100%  by June 2016

Objective 2:  By June 2016, 100% of teachers will use the Aeries Grade Book and the district will offer all parents password protected, online access to up-to-date student attendance, assignments, and grades on the district’s web-based student information system (SIS) (Aeries ABI Grade Book).

Annual Benchmarks for Objective 2

Year 1: minimum of 60% by June 2012	Year 3: minimum of 80% by June 2014

Year 2: minimum of 70% by June 2013	Year 4: minimum of 90% by June 2015

Year 5:  minimum of 100%  by June 2016

Goal 5: Evaluation Instrument(s) & Data

Instrument: Ongoing “how to access” district SIS communications and/ or trainings, parent password requests, and parent usage records.

Data: % of parents trained; % of parents requesting passwords; % of parents using parent component of Aeries

Instrument: Ed Tech Survey data.

Data: % of teachers who self report an increase in the use of the Aeries ABI Grade Book to improve two-way communication

Instrument: District, school, and teacher websites and communication artifacts

Data: evidence of efforts to improve two-way communication

Data reviewers

District Technology Coordinator, site administrators and Media Center/ Library staff will analyze end of school year results annually between June and September and report to stakeholders annually in October.

Goal 5: Improve Communication Among Home, School, and Community

Implementation Strategies / Timelines

- By fall 2011, the district will design and distribute a standardized district Student at Risk notification template-form letter and policy for use to all teachers.

- By fall 2011, all district schools will be providing all district parents with access and training on using the parent component of the district’s online student information system.

- Annually the LEA and schools will solicit community, business, and/or university partnerships.

- Annually the LEA will communicate to all stakeholders (teachers, paraprofessionals, parents, and students) via a variety of media (web sites, class and school booklets, classroom posters, newsletters).

- Annually, continue to fund and maintain, district and school websites where news, announcement, staff contact information, teacher class information, events, etc. are communicated with students and parents.

- Annually, provide web publishing and desktop publishing training opportunities for teachers and classified staff to learn to publish / communicate on their school web site.

- Annually, provide Web 2.0 application training to teachers and classified staff to improve communication between home, school, and community.

Goal 5: Digital Resources to be Integrated

  - SIS suite: Aeries and ABI.

  - Web publishing software.

  - Word, desktop publishing, and Outlook e-mail.

  - District IT work order management system and equipment inventory database.

Section 3K: Ongoing Monitoring for Continuous Improvement

The district curriculum, data, and technology coordinator, school administrators, and the rest of the technology team will conduct ongoing formative data reviews. The team will meet quarterly to track the development and implementation of all tech plan activities and accomplishments. Between quarterly meetings, pertinent tech plan updates are shared with the district committee members via email.. Modifications to our Tech Plan implementation strategies or timeline are made as needed to support meeting or exceeding our goals by June 2016. The Technology coordinator is responsible for a mid-year tech plan implementation status report to stakeholders in February. Annual summative data analysis and needs assessments are conducted in late August / September after the state releases all relevant district data and schools complete early assessments of incoming students. The Technology coordinator is responsible for an annual summative performance report to stakeholders in October.

# Section 4: Professional Development

4a. Summary of District Teachers’ & Administrators’ Technology Skills

Our Education Technology Plan provides a clear summary of our district teachers’ and administrators’ current technology skills from Ed Tech Profile. Our survey findings are summarized by discrete skills in order to better facilitate professional development planning that meets our identified needs and technology plan goals. Additional district technology integration data can be found in Component 3b of our Technology Plan.

Our district reviews Ed Tech Profile survey data and teacher input annually in the spring to plan for district sponsored professional development activities for the next school year. Schools use their site’s Ed Tech Profile survey data and teacher input annually to plan for site-based professional development needs.

Site Administrators’ Survey Data

School district administrators surveyed indicate that they are at the same intermediate and beginning levels of proficiency as the teachers, as shown in the teacher survey below.  The staff as a whole is intermediate in email skills, word processing, general computer knowledge and skills, and Internet skills.  They are at the introductory level in data base, spreadsheet and presentation software skills.  The number of administrators is very low (two) and the sum total of the technological skills is summarized in the teacher results of the Ed Tech survey.

Implication: Administrators need professional development opportunities in basic Personal Technology proficiencies.

District Teachers’ Survey Data

Thirty of the thirty-seven district teachers took the EdTech on-line survey of technological skills in May of 2010.  The results of that survey as presented in a Fall of 2010 report from EdTech Survey are summarized in the report below, as reported in the Fall of 2010.

The Ed Tech Profile survey data of district teachers indicates that most teachers are at intermediate levels with general computing, Internet, e-mail, and word processing and at the introductory level in presentation, spreadsheet, and database skills.

Implication: Teachers need professional development opportunities in basic Personal Technology proficiencies.

Technology Integration Skills

In addition, to proficiency with productivity applications, 11% of teachers in the district rated themselves proficient with integrating technology in the curriculum to improve student learning on a regular basis, but an additional 29% said that they integrate technology and access student needs on an occasional basis.

Other

More resources need to be allocated to the training and inservice needs for our teachers and staff.  Lack of training, for example, was the primary reason cited when teachers were asked about their use of the DataDirector site and the Aeries ABI Gradebook.

4b. Professional Development Goals, Benchmarks, Timelines, Monitoring, and Evaluation.

The Professional Development Criteria 4b elements are included in the teachers’ and administrators’ professional development action plan charts on the following pages. Our professional development action plans are based on a thorough needs analysis and include clear needs-based goals and measurable objectives that will provide our teachers and administrators with sustained, ongoing professional development necessary to implement the Curriculum Component (Section 3) of our education technology plan.

Goal 1: District teachers will be proficient with the same general grade level NETS technology skills required of their students as well as be proficient with technology integration skills and teacher/ admin. electronic learning and productivity tools.

Goal 2: District administrators and teachers will be proficient with using technology to improve student achievement data collection, analysis, reporting, and decision-making.

Goal 3: District administrators and teachers will be proficient use technology to improve two-way communication between home, school, and community.

Our coordinated education technology professional development will be accomplished with a three-tiered approach based on teachers’ individual technology training needs.

- Annually as needed, we will offer personal proficiency training on NETs skills including general computer knowledge and skills; Internet skills; Email skills; Word processing skills; Presentation software skills; job specific productivity and assessment tools; and Spreadsheet /Database software skills.

- Annually as needed, we will offer professional proficiency training on integrating; NETs student standards in math and ELA curriculum (including information literacy, copyright, and cybersafety); curriculum-based software; adopted textbook supplemental electronic resources; and online resources such as SETS and Calaxy.

- Annually as needed, we will provide technology integration mentor training for district staff at school sites on a rotating basis.

Each fall, the district technology coordinator will schedule a variety of training topics and options during the school year.  Each site will have a site technology integration mentor and will be paid an annual stipend.

We anticipate our ed tech professional development plan will cost the district approximately $1000 annually.  Our district anticipates the ability to provide the ed tech professional development outlined with existing categorical funds and EETT formula grant funds.. In addition, we will maximize the use of existing and free web 2.0 applications and site resources to support the goals and objectives for curriculum, instruction, intervention, and assessment, including but not limited to the following:

- Annual completions of the Ed Tech Profile survey and professional development data analysis to track improvements and training needs.

- Identification, training, and use of low and no cost Internet, video-conferencing and face-to-face learning networks, opportunities and resources.

- National, State and local online research-based strategies and resources will be leveraged and integrated during faculty meetings, collaboration time, and professional development such as: the U.S. Department of Education’s web site What Works Clearinghouse. We will regularly examine and use relevant data from the What Works Clearinghouse (WWC) which was established in 2002 by the U.S. Department of Education's Institute of Education Sciences to provide educators, policymakers, researchers, and the public with a central and trusted source of scientific evidence of what works in education.

- We will also rely on the district, the county office, and CTAP Region 2 resources, and the Statewide Education Technology Services (SETS) which includes: California Learning Resource Network (CLRN- http://www.clrn.org/)- which identifies CDE approved supplemental electronic learning resources that both meet local instructional needs and embody the implementation of California curriculum frameworks and standards; the Technology Information Center for Administrative Leadership (TICAL- http://www.portical.org/) - which helps administrators find technology resources to assist in the day-to-day needs of their jobs; and the Technical Support for Education Technology in Schools (TechSETS- http://www.techsets.com/) - which provides technical professionals in California schools improved access to training, support and other resources.

The professional development criteria 4b. is addressed in the teachers’ and administrators’ professional development action plan charts in the Section 4 pages that follow.

#### Biggs Unified School District

#### Ed. Tech Professional Development

July 1, 2011 – June 30, 2016

Section 4b

Goal 1 –Technology Literacy & Integration

District teachers will be proficient with the same general grade level NETS technology skills required of their students as well as be proficient with technology integration skills and teacher/ admin. electronic learning and productivity tools.

Target Group: Certificated teachers

Goal 1: Specific Measurable Objectives by June 30, 2016

Objective 1:  By June 2016, 100% teachers, who participate in district sponsored educational technology professional development, will become proficient with general technology knowledge and skills, classroom productivity tools, and information literacy skills aligned to the NETs for teachers and NETs for students. All district ELD, Special Education and GATE teachers will become proficient in technology skills and assistive tools for their subgroup populations.

Annual Benchmarks for Objective 1

Year 1: minimum of 60% by June 2012	Year 3: minimum of 80% by June 2014

Year 2: minimum of 70% by June 2013	Year 4: minimum of 90% by June 2015

Year 5:  minimum of 100%  by June 2016

Goal 1: Evaluation Instrument(s) & Data

Instrument: Pre and post Ed Tech Profile completed for all district sponsored Education Technology  professional development programs

Data: Administrators’ and teachers’ self assessed technology and integration skills

Instrument: District and site-based training agendas and records

Data: Professional development participation correlated with proficiency in Ed Tech Profile survey

Data reviewers

District Technology Coordinator, site administrators and Media Center/ Library staff will analyze end of school year results annually between June and September and report to stakeholders annually in October.

Goal 1: Technology Literacy & Integration

Implementation Strategies / Timelines

- Annually in the spring, require administrator and teacher completion of Ed Tech Profile survey by all who participate in district sponsored technology training programs.

- Annually, in June, analyze administrator and teacher Ed Tech Profile survey data to plan for professional development offerings during the following school year.

- Annually, provide Ed Tech Profile workshops to teachers, administrators, and district or site Ed Tech Profile admins.

- Annually in the fall, schedule and promote district sponsored technology workshops for administrators and for teachers during the school year aligned to district curricular goals, the content standards, to the NETs, assistive technology, and to identified Ed Tech Profile professional development needs. Encourage all paraprofessionals to participate in training as well.

- Annually in the fall, schedule and promote district sponsored technology integration and CLRN approved curriculum-based software and resource workshops for Math and ELA teachers by grade bands (K-2, 3-5, 6-8, 9-12) during the school year aligned to the content standards and to identified Ed Tech Profile tech integration needs.

- Annually, the district will train and support site-based Technology Integration Mentors (TIMs) to support teachers, paraprofessionals, and administrators at the site level.

- Annually, provide systematic professional development and collaboration time for site administration and teachers to analyze student achievement data, align standards-based instruction, learn and share best practices in instruction and intervention, including the use of technology and develop periodic benchmark assessments horizontally and vertically through grade levels in the district.

Goal 1: Digital Resources to be Integrated

  - Microsoft Office Suite, e-mail, Internet.

  - Diagnostic reading, writing, and math proficiency software.

  - Peripherals such as LCD projectors, digital cameras, video cameras, and printers.

  - CLRN approved curriculum-based software

  - Online resources including SETs and CDE’s Ed Tech Profile

Goal 2 - Using Technology to Support Data Driven Instruction

District administrators and teachers will be proficient with using technology to improve student achievement data collection, analysis, reporting, and decision-making.

Specific Measurable Objectives by June 30, 2016

Objective 1: By June 2016, 100% of teachers and site administrators will be proficient with using technology to collect and analyze assessment data and with making data-driven decisions to meet individual student academic needs and targeted student interventions.

Annual Benchmarks for Objective 1

Show growth from 2009-10 baseline proficiency data.

Year 1: minimum of 60% by June 2012	Year 3: minimum of 80% by June 2014

Year 2: minimum of 70% by June 2013	Year 4: minimum of 90% by June 2015

Year 5:  minimum of 100%  by June 2016

Goal 2: Evaluation Instrument(s) & Data

Instrument: Annual teacher and admin Ed Tech Profile completions for all district sponsored Education Technology professional development programs.

Data: Administrators’ and teachers’ self assessed use of electronic learning assessment systems and data analysis skills.

Instrument: District and site-based SIS training agendas and records

Data: Professional development participation correlated with proficiency in Ed Tech Profile survey

Instrument:  District electronic learning assessments system training participation records and usage records

Data: % of teachers and administrators trained and using electronic learning assessments system to inform instruction.

Data reviewers

District Technology Coordinator, site administrators and Media Center/ Library staff will analyze end of school year results annually between June and September and report to stakeholders annually in October.

Goal 2: Using Technology to Support Data Driven Instruction

Implementation Strategies / Timelines

- Annually, require administrator and teacher completion of Ed Tech Profile survey by all who participate in district sponsored technology training programs.

- Annually, in June, analyze administrator and teacher Ed Tech Profile survey data to plan for technology integration and electronic productivity tool professional development offerings during the following school year.

- Annually by September, plan professional development opportunities for the year focused on standards-aligned classroom assessments and data-driven decisions that meet individual student academic needs and target student intervention needs. Promote opportunities to teachers through all available communication conduits.

- Annually in the fall, schedule and promote district sponsored technology workshops for administrators and for teachers during the school year on all SIS components as needed.

- Annually in the fall, schedule and promote district sponsored technology workshops for administrators and for teachers during the school year on the district’s web-based student reporting system, including the use of the ABI GradeBook.

- Annually in the fall, schedule and promote district sponsored technology workshops for administrators and for teachers during the school year on the district’s integrated electronic learning assessment system.

- Annually, provide systematic professional development and collaboration time for site administration and teachers to analyze student achievement data, align standards-based instruction, learn and share best practices in instruction and intervention, including the use of technology and develop quarterly assessments horizontally and vertically through grade levels in the district.

Goal 2: Digital Resources to be Integrated

- ABI Gradebook

- Microsoft Office Suite, e-mail, Internet.

- Electronic learning assessment and diagnostic applications

- Peripherals such as LCD projectors, digital cameras, video cameras, and printers.

- Online resources including SETs and CDE’s Ed Tech Profile

Goal 3 – Improve Communication between Home, School, and Community

District site administrators and teachers will learn to use technology to improve two-way communication between home, school, and community.

Target Group: Certificated teachers, administrators, and clerical staff

Goal 3: Specific Measurable Objectives by June 30, 2016

Objective 1: By June 2016, 100% teachers will be proficient with the district’s web publishing application.

Annual Benchmarks for Objective 1

Year 1: minimum of 60% by June 2012	Year 3: minimum of 80% by June 2014

Year 2: minimum of 70% by June 2013	Year 4: minimum of 90% by June 2015

Year 5:  minimum of 100%  by June 2016

Goal 3: Evaluation Instrument(s) & Data

Instruments: District records of the % of teachers with updated web pages communicating timely, pertinent information to parents and students..

Data: % of teachers trained; % of updated, timely web pages for teachers and classrooms.

Instrument: Web pages for teachers and classrooms.

Data: evidence of efforts to improve two-way communication.

Data reviewers

District Technology Coordinator, site administrators and Media Center/ Library staff will analyze end of school year results annually between June and September and report to stakeholders annually in October.

Goal 3 – Improve Communication between Home, School, and Community

Implementation Strategies / Timelines

## Annually, require administrator and teacher completion of Ed Tech Profile survey by all who participate in district sponsored technology training programs.

## Annually, in June, analyze Ed Tech Profile administrator and teacher student information/ data analyses results to plan for professional development offerings during the next school year.

- Annually in the fall, schedule and promote district sponsored technology workshops for administrators, clerical and for teachers on using Microsoft Word and other desktop publishing software.

- Annually in the fall, schedule and promote district sponsored technology workshops for administrators and for teachers on the district’s web-based student information (i.e. Aeries and the ABI Grade Book) and reporting system and client e-mail software (i.e. Outlook).

- Annually in the fall, schedule and promote district sponsored technology workshops for parents.

- By spring 2012, schedule and promote district-sponsored workshops for administrators, clerical, and teachers on district / school web site development using district applications. Continue training annually.

Goal 3: Digital Resources to be Integrated

- Office suite of applications

- District’s Web publishing application (currently we use a crossover of FrontPage and Dreamweaver, but we are analyzing and comparing user-friendly web-based solutions for a Content Management System.

- Email client software and online, remote access.

- Low cost , no cost online resources including SETs

- CDE’s Ed Tech Profile

4C: Ongoing Monitoring for Continuous Improvement

Annual professional development needs assessments at the start of each school year will drive our district’s professional development schedule for that year. The district technology coordinator and curriculum director will track implementation of the ed tech professional development plan monthly and report progress at our monthly district/ site admin meetings. The district curriculum, data, and technology coordinator, school administrators, and the rest of the technology team will conduct ongoing formative data reviews. The team will meet quarterly to track the development and implementation of all tech plan activities and accomplishments. Between quarterly meetings, pertinent tech plan updates are shared with the district via email. Modifications to our Tech Plan activities will be made as needed in order to insure that we meet or exceed our goals by June 2016. The Technology coordinator is responsible for a mid-year tech plan implementation status report to stakeholders annually in February. Annual summative data analysis and professional development needs assessments will be conducted between June and September, after the state releases all relevant district data and schools complete early assessments of incoming students. The Technology coordinator is responsible for an annual summative performance report to stakeholders in October

# Section 5: Infrastructure, Hardware, Software, & Technical Support

5a: Current Status

Below is an outline of the existing hardware, Internet access, infrastructure, electronic learning & assessment resources, and technical support available at our district offices and school sites.

At the Server Room (housed at Biggs High School)

Current Infrastructure & Internet Connectivity

The WAN connection from Butte County Office of Education comes into the server room at Biggs High School.  These two T-1 connections currently provide us with 3 megabits per second of a pipeline out to the Internet, the Butte County Office of Education and to the K12 High Speed Network.  Currently we use 50% of that pipeline and spike at various times throughout the day. We currently do not utilize the network for video conferencing or cloud computing, mainly due to lack of funding and the lack of delivery speed that would be needed.  The district’s internet service is provided by the county office of education.  We receive 79% Erate discount on Erateable services.

Internally, all of the devices in the server room (servers, switches and router) are all connected by gigabit fiber.  All of the other sites and all switches all across our LAN are accomplished via gigabit fiber connections, with the one exception being the Richvale Elementary site, described in more detail below.

Current Hardware

We have a total of eight servers in the server room which serve all our needs for firewall, domain controllers, email, web, SIS, and file/print sharing for the entire district.  All of the servers are HP brand, 2 newer ones recently purchased by the Erate program, Proliant Modle DL380G6,  2  HP Proliant ML370G5 and 2 G6, and lastly 2 older HP Proliant Servers).  These servers are used for DNS/DHCP, SIS, library services, file/printer sharing, Web and email.   We have qualified for Erate services for most of the equipment in this server room, as well as for most of our network infrastructure with an 79% discount.

A new Cisco 2821 router is there as well as 3 switches: Cisco 4912G, a Catylst 350 and a 3750.  We have no wireless devices or access points in the server room.

The appendix page “Network Equipment Inventory, Fall 2010” for a more detailed list of equipment.

Current Telephone System

The phone system is the same throughout the entire school district, district office and all school sites except Richvale.  All of these sites except Richvale are interconnected by fiber optic cabling.  The system uses the following phones:  50 of the classroom phones, Norstar, NT8B14AB-03, M7100, and 20 of the office phones, Nortel Network Norstar, NT8B27AABA, T7316.  We have qualified and received Erate discount for basic telephone service in the past.

Current Electronic Learning, Productivity, Assessment and Student Information System Applications

Since our only server room for the entire district (except for the Richvale site) serves all our LAN and WAN connectivity, all sites for the electronic learning, productivity, assessment, and SIS applications are discussed in this section.

The district is standardized for it’s productivity suite of applications on all site computers with Microsoft Office 2003 and 2007.  Our student information system is Aeries CS, used by all sites and housed in the server room.  Many electronic learning software titles are housed on the district’s file servers including titles such as:  Mavis Beacon Teaches Typing, Typing Tutor, Star and Accelerated Math, Word Cross, Math and Reading Blaster Network, Earobics, Read Naturally, Scholastic Reading Counts/Reading Inventory, and Autodesk licensing services for the CAD program at the high school.

The Follett/Destiny library software, used to manage both textbooks, reading books for our “Sustained Silent Reading” (SSR) program and reference books in the library, serves all the district’s three libraries (Biggs High, Biggs Elementary, and Richvale Elementary).

The district subscribes to the Eureka Career information on-line services, Renaissance Learning for reading and writing curriculum support, Follett/Destiny programs for library and textbook management, and Scholastic Reading Counts/Reading Inventory.  The district also subscribes to EdConnect for automatic phone contact to parents for site-wide and district-wide phone call announcements from district personnel.  That EdConnect software exists on one of our servers for automatic updating of the student list at the EdConnect web site.

Current Technical Support

The district technology coordinator (also a teacher at the high school site) serves as the primary tech support person involving hardware, software and direction of meeting technology needs for the district.  Teachers and staff who have technical problems or questions with their hardware, software, network, or questions about “how to” usually use email to contact the technology coordinator and receive a response within one day.  Many of our teachers help other teachers as well on an as needed basis but not in an ongoing, organized method.

The total amount of Full Time Equivalent (FTE) allocated for the district for technical support, both hardware and software, is 2/3 FTE.

The servers, switches, router and connection to the Internet and K12 High Speed Network are supported by WAN and LAN contracts with the Information Technology Department at Butte County Office of Education.  Personnel from IT there at the county are assigned to respond to problems as they arise.  Response time varies depending on the severity of need.  Network outages involving the entire district or even one site are usually met with a response time of less than an hour.  Problems of less severity are put on an “as needed” basis and may be responded to within a day, week or month, again depending on the severity of the problem.  The county IT department also function as our SQL database management, addressing needs of our SIS local database management and the database connections to other software titles and web sites such as Destiny, Scholastic, EdConnect, and DataDirector.

The current arrangement of having a local teacher serve the teacher/staff needs for technology and relying on the county IT department for bigger problems seems to be meeting most of the technical needs of our staff.  But the need of training/inservice of our staff for software titles and new technologies is not being met.  More resources need to be allocated to the training and inservice needs for our teachers and staff.  Lack of training, for example, was the primary reason cited when teachers were asked about their use of the DataDirector site and the Aeries ABI Gradebook.

At Biggs High, Biggs Elementary, Biggs Middle School, the CDS school and District Office

Current Infrastructure & Internet Connectivity

Each of these sites is identically connected to the server room and thusly to one another by a fiber optic network of switches and connections of 1 gigabit speed.  Each computer is connected to the switches by Ethernet copper cabling currently running at 10/100 megabit speed.  Most are connected at 100 megabit speed, depending on the desktop.  No individual computers or classrooms are connected yet by gigabit copper.  We have received an Erate discount in the past for eligible hardware and services of 79%.

Current Hardware

All of these sites currently use a mix of Cisco and HP switches of varying ages, however the Erate program provided the entire district with new switches during the 2009-10 school year, which are currently being put into use.  These are all Cisco  , providing a backbone of 1 gigabit speed, with delivery to each computer of 100 megabits.  The high school and middle school each have one HP wireless access point (HP Aironet 1200) which are both located in the computer labs at these sites.

There are 192 computers used for instructional purposes at these sites.  A majority of these (163) are older than 48 months.  Only 29 computers are newer than 48 months currently.  Of these newer computers, there are 10 laptops for teacher use in their classrooms.  We have no mobile labs of laptops.  These sites have 4 computer labs.

These sites have a total of 43 printers, 2 scanners, 19 video projectors and 2 document cameras for instructional use in the classrooms, computer labs and libraries.  This does not count the counselor’s offices, administration offices and other clerical/attendance offices.

Include info on Routers, Switches, Firewall, Domain Controllers, Servers, Wireless ….as well as… the # of computers used for instruction only < 48 months and the # > 48 months (See section 3b of tech plan) Include an overview of peripherals available at the site. You can have your IT person create a chart with details as an Appendix.

Current Telephone System

The phone system is described above in the “server room” description.  Again, we have received Erate discounts on eligible hardware and services of 79%.

Current Electronic Learning, Productivity, Assessment and Student Information System Applications

In addition to the applications listed above used district-wide, the high school has specific software titles purchased both locally and by the county office of education ROP program.  The district purchased AutoCAD for the CAD class at the high school.  This includes AutoCAD, 3dsMax, AutoCAD Architecture, Design Review, and Revit.  The ROP program purchased the Adobe Master Collection of sotware titles including Acrobat Pro, AfterEffects, Bridge, Contribute, Dreamweaver, Encore, Fireworks, Flash, Illustrator, OnLocation, PhotoShop, Premiere, and Soundbooth.

Current Technical Support

The technical support for these sites is described in the “server room” section above.

At Richvale Elementary School

Current Infrastructure & Internet Connectivity

Rivhvale Elementary is located approximately 8 miles to the north of Biggs.  This site is connected to the rest of the district by way of one T-1 connection offering 1½ megabits per second. That same connection serves indirectly as the site’s connection to the Internet and K12 High Speed Network via the connections in the server room to the aforementioned two T-1 connections to the county office of education.   The site uses less than ½ of this capacity but spikes to 100% periodically throughout the week.  We have received Erate discounts of 79% on eligible goods and services in the past.

Current Hardware

The site has one Cisco 2621 router and 1 Cisco switch and one older server used for file/printer sharing.  The site has a capacity of 100 megabit speed by way of copper cabling between each computer and the switches. The site has one computer lab.  Refer to Appendix page “Network Equipment Inventory.”

There are 31 computers for instructional purposes at the site, 20 of which are older than 48 months.  The site also has six printers, no scanner, one video projector and no document camera.

Current Telephone System

Richvale Elementary School has a different phone system than the rest of the sites.  The phone system is a Meridain Norstar, KSU  NT5B05DC-93  NT 5B05.  The system uses the following phones: one Wireless Uniden Model PowerMax 5 8ghtz, and seven Meridian Northern Telecom RD1987 phones.  We have received Erate discounts of 79% on eligible goods and services in the past.

Current Electronic Learning, Productivity, Assessment and Student Information System Applications

The same applications exist at Richvale as at the other group of sites listed above.

Current Technical Support

The same exact technical support exists at Richvale as at the other sites mentioned above.

5b: District Needs Over the Next Five Years

Below is an outline of our district’s known needs to support the activities in the Curriculum (Section 3) and Professional Development Components( Section 4) of our tech plan in terms of: Infrastructure, Hardware, Electronic Learning & Assessment Resources/Software, Networking, Telecommunication Infrastructure, physical plant modifications, and technical support needed.

Needs for the District Office and all school sites besides Richvale

Infrastructure & Internet Connectivity Needs

The school district will increase its WAN connection speed in Year 15 of the Erate program (2012-13) to a T-3 connection between the district and the Butte County of Office of Education.  Erate discounts will be applied for concerning this service and installation at 79% discount.  No electrical system upgrades will be needed to increase this WAN speed.

Hardware Needs

Routers, switches, and servers as needed will be upgraded in 2012-13 to take advantage of not only gigabit backbone but also gigabit capacity speed delivered to the workstation with the new switches and technology available.  Erate discounts of 79% will also be applied for concerning this hardware.

One video conference unit will be purchased for the district.  16 LCD projectors will be purchased as well so that every classroom will have a projector.  Six scanners will also be purchased.  Five document cameras (Elmo or other appropriate hardware) will be purchased.

20% of the older computers (48 months or older) will be replaced every year with new or recently refurbished computers, starting with the oldest computers in the district.  To keep up with the aging of the existing computers, this will translate into approximately 40 computers per year for the next 5 years.

Many of the older “ink-jet” printers will be replaced as needed, approximately 10 printers per year.  Printers offering lower printing costs both for black and white and color will be purchased.  Laser printers will be the principal printer to be used in the future for this need.

Telephone System Needs

No upgrades to the current phone system are anticipated at these sites.

Current Electronic Learning, Productivity, Assessment and Student Information System Applications

The current Student Information System will be maintained for the district throughout the term of this technology plan.  Annual maintenance and training costs will be realized by the district.  The existing operating system on the existing computers will be upgraded to Windows 7 or other as needed if the machines are not replaced with newer systems.  The Microsoft Office that exists throughout the district is Office 2003 and 2007, with licensing existing on 60% of the machines for Office 2007.  Approximately 80 copies of the newer Microsoft Office suite will be purchased over the next 5 years.

Existing online subscriptions and software purchase maintenance agreements will be purchased for the following:  Follett/Destiny, Renaissance Learning, Eureka, AutoCAD, Adobe Creative Suite.  A new typing tutorial program will be purchased and maintained by the district for the teaching of keyboarding skills district-wide.

Technical Support Needs

Technical support to the individual teacher and classroom will be expanded.  This is the principal need as teachers have stated in the past.  Lead site “Technical Coordinators” will be identified, at least one existing teacher for each major school site (four total).  These will be existing teachers and hired by way of an appropriate stipend to pay for the extra time needed to coach fellow teachers in the use of the technologies, especially the use of the ABI Gradebook for two-way communication and the DataDirector site for monitoring of student performance and teaching/testing to state standards.

Physical Plant Modifications Needs

No plans to modify.

At Richvale Elementary School

Infrastructure & Internet Connectivity Needs

The WAN in Richvale will also be upgraded to a T-3 connection in 2012-13 and all switches/routers will also be replaced, taking advantage of the newer technologies that deliver gigabit speed from the switch to the individual computer.  Erate discounts of 79% will be used for these services.  No electrical upgrades will be needed for this purpose.

Hardware Needs

The only server at Richvale, used for file and print sharing, will be replace in 2012-13.  The switch and router will also be replaced then using Erate discounts of 79% of all eligible goods and services.

A wireless access point will be installed at the site in 2013 as well.

As indicated above for all site, 20% of all the computers older than 48 months will be replaced per year, meaning that 6 – 10 computers will be replaced annually.

Two video LCD projectors, two document cameras and one scanner will be purchased.

Telephone System Needs

The phone system at Richvale will be replaced in 2012-13.  Both the main controller and individual phones will be replaced, using Erate discounts of 79%.

Current Electronic Learning, Productivity, Assessment and Student Information System Applications

The same upgrades to applications, operating systems, SIS, on line subscriptions will apply to Richvale as mentioned above.

Technical Support Needs

The same technical support improvements at Richvale will be sought for as mentioned above for the other sites.

Physical Plant Modifications Needs

No plans to modify.

5c: Annual Benchmarks, Action Steps, Timelines, and Monitoring

Infrastructure & Internet Connectivity Needs

Annual Benchmarks:

Note:  Due to the nature of the Erate application procedures and the unknown status of the district’s eligibility  for infrastructure, the purchase of the equipment for the connectivity needs improvments may have to occur in one year when we will be eligible for Erate discount, perhaps 1 or 2 years during the period of this technology plan.

Year 5: 100% of all sites upgraded to Gigabit LAN and T-3 WAN or better by June 2016

Action Steps & Timeline:

- Submit Erate 470 form annually in the fall and include router/switch upgrades to Gigabit Ethernet LAN only during the years that the district is eligible for discounts on hardware.

- If Erate application is approved, the selected Erate vendor will upgrade all district school sites to Gigabit LAN or better by June 2016

Hardware Needs: New Computers for Teacher & Student Use

Annual Benchmarks:

Year 1: By June 2012, replace 20% of existing instructional computers > than 48 months old.

Year 2: By June 2013, replace 20% of existing instructional computers > than 48 months old.

Year 3: By June 2014, replace 20% of existing instructional computers > than 48 months old.

Year 4: By June 2015, replace 20% of existing instructional computers > than 48 months old.

Year 5: By June 2016, replace 20% of existing instructional computers > than 48 months old.

Action Steps & Timeline:

- Annually in the spring, the district and school site administrators will include a budget line item for replacing existing instructional computers > than 48 months old.

- Annually in the summer, district and site tech support will label, ghost, and install new computers at school sites and replace or repurpose instructional computers > than 48 months old.

Hardware needs in the classroom other than computers for teacher and student use

Every classroom and computer lab will have access to a digital projection device e.g. LCD projector or interactive whiteboard by June 2016.  There will also be one document camera and at least one scanner at each school site by 2016.  10 printers per year will be purchased to replace old out-dated printers in the district.

Annual Benchmarks:

Year 1: By June 2012, replace 10 printers, purchase 3 LCD projectors, 1 document camera and 1 scanner.

Year 2: By June 2013, replace 10 printers, purchase 3 LCD projectors, 1 document camera, 1 scanner, and 1 video conference unit.

Year 3: By June 2014, replace 10 printers, purchase 3 LCD projectors, 1 document camera and 1 scanner.

Year 4: By June 2015, replace 10 printers, purchase 3 LCD projectors, 1 document camera and 1 scanner.

Year 5: By By June 2016, replace 10 printers, purchase 3 LCD projectors, 1 document camera and 1 scanner.

Action Steps & Timeline:

- Annually in the spring, the district and school site administrators will include a budget line item for replacing existing printers, purchasing LCD projectors, document cameras, scanners and video conference units.

- Annually in the summer, district and site tech support will install these devices in the needed classrooms.

Section 5d: Benchmark Monitoring and Evaluation Process

The District Technology Coordinator and school site administrators will track the accomplishment of benchmarks and the implementation of necessary action steps and inventories. Modifications to our district activities will be made as needed in order to insure that we meet or exceed annual benchmarks. The District Technology Coordinator, school site admins., and school site tech coordinators will conduct ongoing formative data reviews. Pertinent tech plan and funding updates are shared with the district and school site tech support via emailt. The technology committee will meet quarterly to track the development and implementation of all tech plan activities and accomplishments. Modifications to our Tech Plan activities will be made as needed in order to insure that we meet or exceed our goals by June 2016. The Technology coordinator is responsible for a mid-year tech plan implementation status report to stakeholders annually in February. Annual summative data analysis and professional development needs assessments will be conducted between June and September, after the state releases all relevant district data and schools complete early assessments of incoming students. The Technology coordinator is responsible for an annual summative performance report to stakeholders in October.

# Section 6: Education Technology Funding & Budget

6a. Established and Potential Funding Sources

Established Funding Sources

Economic conditions in California and the nation continue to impact our district’s education budgets . Therefore, our established and potential funding sources to implement our Ed. Technology Plan will likely be impacted as well.  Our school district receives varied federal, state, and local sources of funding.  These include state Tier 3 categorical funds, lottery funds, Microsoft K12 Vouchers, Erate discounts, a variety of federal ESEA Title funds, and miscellaneous grants.  We also receive donations from the community members and businesses. The continued need for up-to-date student and teacher computers (4 years old or newer) and for site-based technical help are the biggest budget challenges for technology in our district.

The district General Fund covers the costs for:

- The salaries for the district’s Information Technology Services staff

- The district’s student information system (SIS), including implementation & training costs.

- The district’s student learning assessment system, including implementation & training costs

- Telecommunication services such as phone and internet connectivity that are not covered by Erate.

- Equipment, resources, and tools used by the district’s Information Technology Services department.

- Upgrades to district supported digital learning and productivity applications

- Network Security applications

The District’s Ed Tech Funds Pay For:

- Education technology staff development for teachers, administrators, paraprofessionals, and classified staff to meet Ed Tech curricular goals in district tech plan.

- Training costs for our IT technical staff

- Extra technical help deployment for special district projects.

- Some costs for new hardware and peripherals if the district’s ed tech budget allows.

Site-based Funds Pay For:

School sites often choose to pay for site-based technical support, digital teaching and learning applications, additional computers & peripherals, etc. as individual site-based needs dictate and budgets allow.

District Erate Discount as of Fall 2010

79%

Potential NEW Funding Sources

Potential additional funding sources include additional K12 Vouchers to be released to Round One voucher applicants; EETT Formula funds; new Federal, State, and Private Grants; in-kind services; fundraisers; and donations.

Given the uncertainty of our Ed Tech sources of funding, we have established the following priorities list to guide district budget allocation:

- Increase student and teacher access to computers < 48 months old.

- Provide Ed Tech Staff development for teachers, paraprofessional, and classified staff.

- Upgrade infrastructure

- Improve technical support at school sites and reduce response time

- Purchase online subscriptions to curricular and assessment systems

- Provide Ed Tech Staff development for administrators

- Increase the use of communication with parents via the ABI Gradebook, requiring training for teachers.

- Increase the use of DataDirector among staff for data-driven decision making in the classroom instruction and testing

6b. Estimate of Annual Implementation Costs

While the charts that follow project realistic total costs of implementing our district’s technology plan, actual amounts the district office will expend will be contingent on annual fiscal realities as well as competing district office priorities. During the summer and early fall of each school year, we will review, revise, and update our tech plan to align with our annual Ed Tech budget realities.

| Category | Projected Ed Tech Expenditures 2011-12 | Estimated TCO Year One | ERATE* Eligible Amount? | Year 1 Funding Source(s) for Non ERATE Eligible Amt. |
| --- | --- | --- | --- | --- |
| 1000-1999 Certificated Salaries | Substitutes and stipends for staff development ($1,500 substitutes, 3 site trainers at $500 each) | $3000 | N/ A | District Ed Tech Budget |
| 2000-2999 Classified Salaries | Tech Support Salaries | $32,789 | N/ A | District General Fund |
| 3000-3999 Employee Benefits | Tech Support Benefits | $6,383 | N/ A | District General Fund |
| 4000-4999 Books and Supplies | New & Refurbished Computers | $10,000 | N/ A | District & School Budgets |
|  | Misc. Peripherals: LCD Projectors, Printers, Document Cameras, Scanners | $9,500 | N/ A | District & School Budgets |
|  | Productivity Applications (Office, Security) | $2,000 | N/ A | District General Fund |
|  | Digital curriculum & library resources: Destiny, Renaissance, Eureka, Star Math, Scholastic | $2,000 | N/ A | District & School Budgets |
|  | Student Achievement Formative Assessment System (e.g. DataDirector) | $7,500 | N/ A | District General Fund |
| 5000 -5999 Services, operating expenses, travel | Telecommunication Services (e.g. phone) | $19,900 | $13,900 | District General Fund |
|  | Telecommunication Services, WAN contract | $15,000 | $11,850 | District General Fund |
|  | Misc.Networking and Telecommunication Infrastructure and support, LAN Contract w/ Butte County Office of Education | $6,300 | $3525 | District General Fund |
|  | Cisco Maintenance (contract switches/routers) | $3,000 | $2370 | District General Fund |
|  | Annual cost of SIS program, Aeries | $4,400 |  |  |
| 6000 -6999 Capital Outlay | None |  | N/ A | District General Fund |
| Totals: |  | $121,772 TCO | - $31,645 -- Erate Discount | = $ 90,127 TCO minus Erate Discount |

(*see district’s annual ERATE budget supplement for details)

Our district has estimated the Total Cost of Ownership (TCO) of our Ed Tech Plan accounting for all the major cost factors over the duration of the plan. Please note that all of the budget figures in the chart that follows are TCO estimates and will only be expended if funding is available.

| Total Cost of Ownership for 5 year Tech Plan | yr 1 | yr 2 | yr 3 | yr 4 | yr 5 |
| --- | --- | --- | --- | --- | --- |
| Ed Tech Professional Development Substitutes & Stipends | 3,000 | 3,000 | 3,000 | 3,000 | 3,000 |
| TCO District Funded Technical Support & Benefits | 39,172 | 39,172 | 39,172 | 39,172 | 39,172 |
| TCO Hardware and Peripherals (Refurbished Computers: 10,000 , Peripherals: 9500, Network equipment year 2: 23940) | 19,500 | 43,400 | 19,500 | 19,500 | 19,500 |
| TCO Digital Applications,Upgrades, and Online Subscription Services | 4,000 | 4,000 | 4,000 | 4,000 | 4,000 |
| TCO Student Achievement Formative Assessment System (e.g. DataDirector) | 7,500 | 7,500 | 7,500 | 7,500 | 7,500 |
| TCO Student Information System (SIS) | 4,400 | 4,400 | 4,400 | 4,400 | 4,400 |
| TCO Networking and Telecommunications w/ Erate Discounted Services e.g. Network / Infrastructure Services, Internet Access, Web site services (Phone, WAN: 3150, | 9780 | 11780 | 11780 | 11780 | 11780 |
| TCO Other Contracted Services e.g. Prof.Development, Tech Support, Retrofitting, out sourced maintenance. LAN Contract 2775 | 2775 | 2775 | 2775 | 2775 | 2775 |
| Total Estimated Cost Per Year | 90,127 | 116,027 | 92,127 | 92,127 | 92,127 |
| Five Year Total Cost of Ownership Cost Estimate* (Based on goals, objectives, and action steps in Tech Plan sections 3, 4, & 5.) | $ 482,535 |  |  |  |  |
| *Potential Annual Erate discounts are included in TCO in this chart. |  |  |  |  |  |

6c. District’s Replacement Policy for Obsolete Equipment

The district’s replacement policy for obsolete equipment is to replace all computers that are more than four years old, but ultimately, replacement is dependent on annual fiscal realities as well as district priorities each academic school year. Site administrators work with the district technology staff to determine whether the obsolete computers can be repurposed for less demanding applications or upgraded, or whether they are no longer able to support any of the current programs and processes that are required to implement the curricular goals of the school. If the computers cannot be repurposed at the site or worth upgrading, the equipment is deemed obsolete. A local computer refurbishing entity picks-up any re-useable electronic components at no cost to the district.

6d. District’s Budget and Funding Monitoring Process

Our district is committed to a dependable and sustainable technology plan that ensures funding for reliable infrastructure, hardware, technical support, professional development, and software for all district school sites.

The district superintendent, school board, Technology coordinator and Site Administrators have the primary responsibility for funding goals and objectives specified in this plan. In addition, the district technology committee reviews the ed tech budget and purchases during regularly scheduled quarterly meetings and provides input on any budget adjustments that are deemed necessary by the Superintendent and the Technology coordinator.

The Technology coordinator is responsible for taking budget recommendations and revision requests to cabinet-level meetings and the School Board as needed. The Chief Business director monitors ed tech implementation costs as part of the district’s regular budget and purchase order processing. The Technology coordinator, technology committee, and parent organizations routinely research new funding opportunities for district education technology. School site technology budgets are the domain of site principals and school site councils.

# Section 7: Monitoring & Evaluation of Technology Plan

7a. Evaluation Process

In order to maintain the accuracy and relevance of our education technology plan, it is essential to monitor and if necessary revise each component of this plan on an ongoing basis. Ongoing collection of data and the use of that data to inform decision-making and continuous improvement is embedded in our tech plan components under the monitoring and evaluation components in sections 3, 4, & 5. These sections of the tech plan include specific evaluation instruments and data that will be collected on an ongoing basis and analyzed annually to assess the tech plan’s impact on teaching and learning.

Each identified objective in our Technology Plan will be reviewed and evaluated monthly by the District Technology Coordinator, who has the overarching responsibility for ensuring that our goals and objectives are monitored, adjusted as necessary, and ultimately achieved. In addition, the district’s technology committee will track the development and implementation of all activities and accomplishments during quarterly meetings as well as review the latest data and any needed revisions to the plan. Between meetings, the District Technology Coordinator communicates tech planning issues and setbacks to committee members and solicits feedback via e-mail and voice-mail on an ongoing basis.

7b. & 7c.: Annual Monitoring, Evaluation and Communication of Tech Plan

The following chart specifies the monitoring and evaluation annual timeline as well as the process and frequency of communicating results to tech plan stakeholders.

Annual Monitoring, Evaluation and Communication of Tech Plan Implementation and Impact

| Person(s) Responsible | Process | Monitoring | Evaluation |
| --- | --- | --- | --- |
| District Technology Coordinator & Tech. Committee | Provide overall Tech Plan management and coordination | Ongoing | Ongoing |
| District Technology Coordinator, Tech. Committee, and Curriculum Director | Manage, coordinate, implement, monitor, and evaluate curriculum-based technology integration staff development. | Ongoing | Annually in June |
| District Technology Coordinator, Tech. Committee, and Curriculum Director | Manage, coordinate, implement, monitor, and evaluate staff development focused on teaching students NETS skills. | Ongoing | Annually in June |
| District Technology Coordinator & Tech. Committee | Coordinate, manage, and evaluate technology budget, acquisitions, installation, and maintenance. | Ongoing | Annually in August |
| District Superintendent, Technology coordinator, & Tech. Committee | Standardize, develop, manage, monitor, and revise as necessary network, hardware, infrastructure, software, and technical support specifications, policies, and procedures. | Ongoing | Annually in August |
| District Superintendent, Technology coordinator, & Tech. Committee | Collect and analyze staff development data on technology proficiencies through the annual completion of district survey. | Ongoing | Annually in June |
| District Superintendent, Technology coordinator, & Tech. Committee | Coordinate ongoing tech committee and stakeholder involvement. | Ongoing | Annually in August |
| District Technology Coordinator, Tech. Committee, and Data Director | Collect and analyze data regarding students’ NETS skills and students’ academic achievement | Ongoing | Annually in August |
| District Superintendent and Technology coordinator | Communicating tech plan implementation update to stakeholders including the district school board. | Minimally semi-annually in February | N/A |
| District Superintendent and Technology coordinator | Communicating annual tech plan evaluation results to stakeholders including the district school board. Parentsand the community will receive annual reports via the district web site, newsletters, and press releases. | N /A | Annually in October after all tech plan data for the year is in. |

# Section 8: Adult Literacy and Technology

Our district does not provide adult literacy education nor are there any nearby adult literacy providers or community colleges within commuting distance of our district. However, the county office does run a Regional Occupational Program (ROP) that offers a variety of technology and adult training opportunities. These free ROP classes are open to all residents of the county, who are at least 16 years old. Classes are offered mornings, afternoons and evenings, at district offices and high school campuses in the region. This flexible training program provides adults with career guidance, hands-on training, and job placement assistance. Our District Technology Coordinator will meet with the county ROP director annually in June to discuss the possibility of additional outreach efforts in our district, including the possibility of using technology to provide adult literacy services in our district.

# Section 9: Effective, Research-Based Strategies

9a. Effective technology strategies for student learning, teaching, and management

Our technology plan lists clear goals and strategies for integrating technology into the curriculum to improve student learning in the specific areas of English/ Language Arts and Math.  The learning objectives are based on the California State Academic Content Standards.

The following relevant research was examined and integrated into our plan. The research we selected emphasizes best practices for technology integration in the curriculum, Total Cost of Ownership, and important factors that contribute to successful staff development.

During the course of our district’s tech planning process, our technology committee reviewed several research-based documents to inform the planning efforts. What follows is a brief summary of the major findings that have been integrated in our 2011-2016 tech plan.

District Education Technology Vision Building

One of the recent research reports that we reviewed as we began our planning process was, “The 2010 Horizon Report: K-12 Edition”, a publication of The New Media Consortium. The Horizon Reports are an ongoing research effort established in 2002 that identifies and describes emerging technologies likely to have a large impact on teaching, learning, research, or creative expression within education around the globe. This volume of the 2010 Horizon Report: K-12 Edition, examines emerging technologies for their potential impact on and use in teaching, learning, and creative expression within the environment of pre-college education. Cloud computing and collaborative learning environments are set to take hold in K-12 schools in the very near future, with mobile devices, game-based learning, and other education technologies to follow suit in the next few years, according to the 2010 Horizon Report’s K-12 Edition. Our committee spent a large amount of time talking about these emerging technologies in our district and translated those conversations into the district’s education technology vision and 5-year tech plan with an emphasis on exploring cloud computing options and collaborative environments.

Teachers’ Use of Technology

We looked at several research-based sources that supported our plans in this area. After our initial efforts in technology, during the timeframe of the District’s previous technology plan, it became clear that just providing teachers with access to technology did not necessarily result in a high level of usage in the classroom. The literature is very clear about this – successful integration of technology into the classroom requires the availability of quality technology support. Support is defined in a multifaceted way, comprising elements like access to technological tools (software and hardware), routine maintenance and specific, individualized training. In a study that we found from the National Center for Education Statistics teachers identified several “barriers” to the use of computers for instruction. These barriers included not having enough computers in their classrooms, a lack of time in their schedule for students to use computers in the classroom, and a lack of release time for teachers to learn how to use computers. These issues are addressed in our plan through the comprehensive professional development component, the establishment of a department that will support instructional technology use in the district, and the plan for increasing access to district-adopted hardware and software for teachers – among other things.

Specific conditions affect the positive influence technology can have on student academic achievement. Several sources agree that a critical component is providing appropriate teacher training in ways to effectively integrate technology into the curriculum, focusing on meaningful educational goals and improving student learning. (Glennan and Melmed, 1996, Silverstein et al, 2000, Reksten, 2000, Coley, 1997, Panuel b, Golan, Means, B and Korbak, c. 2000)

Infusing technology across the curriculum allows students to take more responsibility for their learning and teachers to create more meaningful and diverse learning activities. Through research on the Internet, communication with others through e-mail, analysis of information using databases, making oral reports using presentation software, producing written reports with word processing software and collaborating with peers, students will become confident problem-solvers and critical thinkers. This is particularly relevant, as recognized by Penuel et. al. “Students using sophisticated technologies as everyday learning tools show marked growth in essential workplace skill. Moreover, such gains do not come at the expense of basic skills.” (Penuel, Golan, Means & Korbak, 2000)

In support of this conclusion, a recent study conducted in West Virginia, “shows an increase in test scores resulting from integrating curriculum objectives for basic skills development in reading and mathematics with instructional software” (Cradler et al., 2002).

A two-year study conducted by the Southwest Educational Development Laboratory (SEDL) focused on helping teachers create a learner-centered learning environment supported by technology. The conclusions revealed that while initially 47% of the classrooms in the study were classified as “low learner-centered classrooms” only 15% were given that label when the project was complete. The types of professional development offered to teachers influenced the transformation. 72 hours of training sessions were held in classrooms similar to those the teachers taught in to replicate the teaching environments they would use for instruction. Sessions offered many opportunities for a sharing of learning and reflecting on the learning process. Monthly on-site visits to classroom by SEDL staff members were essential to the success of the project.

As stated in the study, “The process of learning how to use and integrate technology created a new dynamic of learning for teachers and affected their ways they related to content, to their colleagues, and to their students. Finally, technology use had a cumulative effect on the project teachers in a school. Their enthusiasm about technology served as the impetus for their more reluctant or more skeptical colleagues to attempt to use technology in their classrooms – especially when student performance increased.” (Burns 2002)

Teacher expertise is the most critical factor in increasing student performance. Nothing impacts student success in a standards-based curriculum more than a competent, reflective teacher in the classroom who interacts effectively with students, facilitates their learning experiences, and uses curriculum and curriculum materials effectively (Cohen and Ball 1999). As Guhlin states, “For technology to impact student achievement, teachers must be empowered” (Guhlin 2002). They must also be completely at ease with the technologies the students are using, and they should be proactive about planning for effective technology integration.

Jerald and Orlafsky (1999) found that teachers “are more likely to use what they are learning about technology in their classrooms if they receive curriculum integration training rather than basic skills training in the use of technology.” A later study (Bradshaw 2002) found that “When staff development efforts include a presentation of theory and information, demonstration, practice with feedback, and coaching and follow-up over time, the transfer to the classroom and the return on the investment in instructional improvement are significantly increased.” All of these techniques are woven into the district’s current staff development programs in technology.

Impact of Technology on Instruction and Student Achievement

We looked at the potential impact of technology on student achievement as we developed our plan. Certainly, with the cost of most computers and other technological learning tools, impact on student achievement is an important consideration for a district as it looks for funds to invest in this effort. We found several studies addressing this issue. What follows is a brief summary of a few.

Teacher capability was important in research by Wenglinsky (1998). Using the technique of structural equation modeling on data from the 1996 National Assessment of Educational Progress (NAEP), he conducted a study analyzing the relationship between educational technology and student achievement in mathematics. His findings indicate that, "when computers are used to perform certain tasks, namely applying higher order concepts, and when teachers are proficient enough in computer use to direct students toward productive uses more generally, computers do seem to be associated with significant gains in mathematics achievement" (p. 32). Wenglinsky also found that the frequency of home computer use was positively related to academic achievement.

In a study of educational software, IESD (1999), found the teacher's responsibility is of primary importance in "creating an effective, technology-based learning environment, an environment that is characterized by careful planning and frequent interaction among students and the teacher" (p. 3). Middleton and Murray (1999), in a study investigating teachers' perceptions of their levels of technology implementation, found that the level of technology used by the teacher did have a significant impact on math and reading academic achievement of fifth grade students attending schools in a South Carolina school district.

A national study examining the role of online communication in schools was conducted by the Center for Applied Special Technologies. The study consisted of 500 elementary and middle school students from seven large urban school districts who were assigned projects in an interdisciplinary unit on civil rights. Out of 28 participating classes, 14 experimental classes used online resources and 14 control classes did not have online access. In this study, Follansbee et al. (1997), found that students in the experimental classrooms received higher scores in all nine of the established learning measures. Out of the nine measures, five of the higher scores were found to be statistically significant including being more effective in their ability to, "present their work, state a civil rights issue, present a full picture (who, what, when, where, why, how) bring together different points of view, and produce a complete project" (p. 18).

In research on educational technology and software, an IESD study unequivocally proclaims, "educational technology has demonstrated a significant positive effect on achievement. Positive effects have been found for all major subject areas, in preschool through higher education and for both regular education and special needs students" (1999, p. 3).

In a related summary of current research findings regarding technology in education, Cradler (1994, p. 1) found research that shows technology:

- Increases performance when interactivity is prominent.

- Improves attitude and confidence, especially for "at-risk" students.

- Can increase opportunities for student-constructed learning.

- Increases student collaboration on projects.

- Significantly improves problem-solving skills of learning handicap students.

- Improves writing skills and attitudes about writing for urban LEP students.

Student performance is the catalyst for change. One study cited reports that the project group of students “routinely employed inquiry, collaborative, technological, and problem-solving skills uncommon to graduates of traditional high school programs” (Sandholtz, et all., 1997). In another study, researchers investigated the impact of project-based learning using multimedia (Penuel, Golan, Means, & Korbak, 2000). Project classrooms in this study were much more student-centered than non-project classrooms, and were “organized around the collaborative construction of complex products” (Penuel et al., 2000. p. 109).

Using technology in a constructivist environment either in individual student-centered projects or in collaborative group-work is powerful, as summarized by Means: “Student motivation is enhanced through online collaborative research that includes online communication with peers and experts in other states and countries” (Means et al., 1997). Cradler agrees. “Students and teachers reported a positive change in student motivation for class assignments when the use of multimedia was incorporated into classroom instruction” (Cradler & Cradler, 1999).

Von Secker (2002) reports that inquiry-based learning has been shown to increase both academic outcomes and equity. Computers function as extremely powerful tools for self-directed learning and are particularly well suited for enabling the objectives of constructivist principles (Jonassen & Reeves, 1996). Marzano, Pickering and Pollock add that through constructing their own meaning around authentic issues, students acquire the sophisticated thinking skills needed to live and work in the 21st century (2001). This in itself requires innovative strategies in the teaching/learning process.

Our technology committee has concluded that for technology to make a lasting impact educators must use a variety of teaching and learning approaches when utilizing technology in their classrooms. Time and again, the research comes back to the teacher as the most influential component of a successful technology program. Teachers must be given the time and resources to attend professional development opportunities on utilizing technology in the classroom. Schools should make the most of teachers who are "resident experts" that can offer on-site development opportunities and be used as one-on-one tutors for other faculty members. Our plan addresses this issue in several places, calling for planning time, development of units of practice that integrate technology as a learning tool, and development of technology experts through training opportunities.

Data-driven Decision Making

Several sources we studied addressed the importance of using technology to assist administrators, teachers, parents and students make decisions about teaching, learning and program development based on data. Goals should include:

- Establishment of a foundational understanding of data collection

- Make connections to existing data collections

- Identify relevancy of data to school improvement efforts

The National School District has made great progress in establishing a data management system for purpose of facilitating the use of data to make quality decision about instructional programs. This will continue to be a major focus of the plan during the next five years.

Research has shown that with computer-aided instruction, student academic achievement improves. Underwood and Brown have shown a correlation between computer-based instruction and student motivation for learning. The ease of error correction, a semi-private environment, active control, and ability to work at one’s own pace all increase student motivation. (1997). Cotton adds that “computer-assisted instruction resulted in improved student attitudes in a variety of areas. These areas included improved attitudes towards themselves as learners, the use of computers in education, course subject matter, quality of instruction, and school in general” (1992).

## 9B. Using Technology to Expand Access to Curriculum

Our District is examining ways to deliver curriculum and professional development using new, innovative, technology-based tools.  Our Technology Plan integrates the development of innovative strategies for using technology including the use of free or low cost online resources, cloud computing, Open Source and Web 2.0 tools and resources for students, teachers, and administrators such as those offered on Calaxy (http://www.k12hsn.org/calaxy/ ) via the California K12 High Speed Network.  We will continue to work with CTAP Region 2 and our County Office of Education to explore use of the K12 High Speed Network to deliver rigorous academic curriculum online to our students.

Bibliography

Archer, J. (1998). The link to higher test scores. Education Week, 18 (5), 10-21.

Bare, J., and Meek, A. (1998). Internet Access in Public Schools (NCES 98–031). U.S. Department of Education. Washington, DC: National Center for Education Statistics.

Bradshaw, L. (2002). "Technology for Teaching and Learning: Strategies for Staff Development and Follow-Up Support." Journal of Technology and Teacher Education 10(1): 131-150.

Cattagni, A., and Farris, E. (2001). Internet Access in U.S. Public Schools and Classrooms: 1994– 2000 (NCES 2001–071). U.S. Department of Education. Washington, DC: National Center for Education Statistics.

Cohen, D. K. and D. L. Ball (1999). Instruction, Capacity and Improvement. Consortium for Policy Research in Education. Philadelphia, PA, University of Pennsylvania.

Cotton, K. (1992). Computer-assisted instruction. Northwest Regional Educational Labratory. Retrieved October 26, 2001, from http://www.nwrel.org/scpd/sirs/5/cu10.html

Cradler, J., & Cradler, R. (1999). Just in time: A new model for multimedia training. Evaluation report for 1999. Washington DC: US Office of Education.

Cradler, J., M. McNabb, et al. (2002). "How Does Technology Influence Student Learning?" Learning and Leading With Technology 29(8): 46-50.

Cradler, J. (1994). Summary of current research and evaluation findings on technology in education. San Francisco, CA: Far West Laboratory.

Cradler, J., & Bridgforth, E. (1996). Recent research on the effects of technology on teaching and learning. Policy Brief. San Francisco, CA: WestEd Regional Educational Laboratory.

Critical issue: Using technology to improve student achievement. (1999). Retrieved December 14, 2002, from North Central Regional Educational Laboratory Web site: http://www.ncrel.org/sdrs/areas/issues/methods/technlgy/te800.htm

Culp, K., Hawkins, J., & Honey, M. (1999). Review paper on education technology research and development. New York: Education Development Center, Center for Children and Technology.

Department of Education, National Center for Education Statistics. Washington, DC: U.S., Government Printing Office. Special Education Regulation, 34 C.F.R. Sec. 300.26 (2001).

Education, I. S. f. T. i. (2000). National Educational Technology Standards for Students: Connecting Curriculum and Technology. Eugene, OR, International Society for Technology in Education.

Follansbee, S., Hughes, R., Pisha, B., & Stahl, S. (1997). Can online communications improve student performance? Results of a controlled study. ERS Spectrum, 15 (1), 15-26.

Guhlin, M. (2002). "Teachers Must Push Technology's Tidal Wave." Journal of Staff Development 1(Winter): 40-41.

Heaviside, S., and Farris, E. (1997). Advanced Telecommunications in U.S. Private Schools, K–12, Fall 1995 (NCES 97–394). U.S. Department of Education, National Center for Education Statistics. Washington, DC: U.S. Government Printing Office.

Heaviside, S., Farris, E., and Malitz, G. (1995). Advanced Telecommunications in U.S. Public Schools, K–12 (NCES 95–731). U.S. Department of Education. Washington, DC: National Center for Education Statistics.

Heaviside, S., Farris, E., and Malitz, G. (1996). Advanced Telecommunications in U.S. Public Elementary and Secondary Schools, 1995 (NCES 96–854). U.S. Department of Education. Washington, DC: National Center for Education Statistics.

Heaviside, S., Riggins, T., and Farris, E. (1997). Advanced Telecommunications in U.S. Public Elementary and Secondary Schools, Fall 1996 (NCES 97–944). U.S. Department of Education. Washington, DC: National Center for Education Statistics.

Heaviside, S., Rowand, C., Hurst, D., and McArthur, E. (2000). What Are the Barriers to the Use of Advanced Telecommunications for Students With Disabilities in Public Schools? (NCES 2000– 042). U.S. Department of Education. Washington, DC: National Center for Education Statistics.

Hennessy, S. et al. (1995). A classroom intervention using a computer-augmented curriculum for mechanics. International Journal of Science Education, 17(2), 189-206.

Honey, M., & Henriquez, A. (1996). Union city interactive multimedia education trial: 1993-1995 summary report. CCT Reports, Issue No. 3. New York, NY: Center for Children & Technology.

Hord, S. M. and Association for Supervision and Curriculum Development. (1987). Taking charge of change. Alexandria, Va., Association for Supervision and Curriculum Development.

Interactive Educational Systems Design, Inc. (IESD). (1999). 1999 Research report on the effectiveness of technology in schools: Executive summary 6th edition. Report commissioned by the Software & Information Industry Association. Washington, DC: Software Publishers Association.

James, R., & Lamb, C. (2000). Integrating science, mathematics, and technology in middle school technology-rich environments: A study of implementation and change. School Science & Mathematics, 100 (1), 27-36.

Jerald, C. D. and G. F. Orlafsky (1999). "Across the Nation: Raising the Bar on School Technology." Education Week 19(4): 58-108.

Kulik, J. (1994). Meta-analytic studies of findings on computer-based instruction. In E. L. Baker and H. F. O'Neil, Jr. (Eds.). Technology assessment in education and training. Hillsdale, NJ: Lawrence Erlbaum.

Lampert, L. (1998). Building Leadership Capacity in Schools. Alexandria, VA, Association for Supervision and Curriculum Development.

Lanahan, L. (2002). Beyond School-Level Internet Access: Support for Instructional Use of Technology (NCES 2002–029). U.S. Department of Education. Washington, DC: National Center for Education Statistics.

Levin, D., Hurst, D., and Burns, S. (2000). Computer and Internet Access in U.S. Private Schools and Classrooms: 1995 and 1998 (NCES 2000–044). U.S. Department of Education. Washington, DC: National Center for Education Statistics.

National Middle School Association (1995). This we believe: Developmentally responsive middle level schools. Columbus, OH: Author.

Newburger, E. (2001). Home Computers and Internet Use in the United States: August 2000. U.S. Census Bureau, Current Population Reports, August 2000.

North Central Regional Educational Laboratory (1999). Hands-on, minds-on learning. ParenTech: Parenting in a Digital Age. Oak Brook, IL: NCREL.

Mann, D., Shakeshaft, C., Becker, J., & Kottkamp, R. (1999). West Virginia's basic skills/computer education program: An analysis of student achievement. Santa Monica, CA: Milken Family Foundation.

Marzano, R., D. Pickering, et al. (2001). Classroom Instruction that Works: Research-based Strategies for Increasing Student Achievement. Alexandria, VA, Association for Supervision and Curriculum Development.

Means, B. (1994). Technology and education reform: The reality behind the promise. San Francisco: Jossey Bass.Oxford, UK: Heinemann/NCET.

Means, B., Coleman, E., Klewis, A., Quellamlz, E., Marder, C., & Valdes, K. (1997). Globe Year 2 Evaluation. Menlo Park, CA: SRI International.

Middleton, B., & Murray, R. (1999). The impact of instructional technology on student academic achievement in reading and mathematics. International Journal of Instructional Media, 26 (1), 109- 117.

Munger, L. and K. Pensick (2002). Cross-Case Analysis: Six Technology Innovation Challenge Grants from Five Western Cluster Sites. Arvada, CO, National Staff Development Council: 1-166.

Parsad, B., Skinner, R., and Farris, E. (2001). Advanced Telecommunications in U.S. Private Schools: 1998-99 (NCES 2001–037). U.S. Department of Education, National Center for Education Statistics. Washington, DC: U.S. Government Printing Office. President’s Committee of Advisors on Science and Technology, Panel on Educational Technology. (1997).

Penuel, B., Golan, S., Means, B., & Korbak, C. (2000). Silicon Valley Challenge 2000: Year 4 Report. Menlo Park, CA: SRI International.

Report to the President on the Use of Technology to Strengthen K–12 Education in the United States. Available: http://www.ostp.gov/PCAST/k-12ed.html.

Ross, John D., Burdette, Krista J (2001). Toward an Effective Use of Technology in Education: A Summary of Research. Appalachia Educational Laboratory, Incorporated.

Rowand, C. (1999). Internet Access in Public Schools and Classrooms: 1994–98 (NCES 1999–017). U.S. Department of Education. Washington, DC: National Center for Education Statistics.

Sandholz, J. H., Ringstaff, C., & Dwyer, D. C. (1997) Teaching with technology: Creating student-centered classrooms. New York: Teachers College Press.

Schrum, Lynne. (Jan. 2000). Let’s Put Pedogogy First: Technology as a Tool to Support Instruction. Retrieved Jan. 6. 2003, for Education World Website: http://www.educationworld.com/a_tech/tech004.shmtl.

Secretary’s Commission on Achieving Necessary Skills. (1991). What work requires of schools: A SCANS report for America 2000. Washington, DC: US Department of Labor.

Sivin-Kachala, J. (1998). Report on the effectiveness of technology in schools, 1990-1997. Washington, DC: Software Publisher's Association.

Smerdon, B., Cronen, S., Lanahan, L., Anderson, J., Iannotti, N., and Angeles, J. (2000). Teachers’ Tools for the 21st Century: A Report on Teachers’ Use of Technology (NCES 2000–102). U.S.

Thornberg, David. (2002). The New Basics: Education and the Future of Work in the Telematic Age. Alexandria, Virginia: ASCD.

Underwood, J., & Brown, J. (Eds.). (1997). Integrated learning systems: Potential into practice. Oxford, UK: Heinemann/NCET.

Von Secker, C. (2002). "Effects of Inquiry-Based Teacher Practices on Science Excellence and Equity." The Journal of Educational Research 95(3): 151-60.

Wade, H. H. (2002). "Data Inquiry and Analysis for Educational Reform." ERIC Digest: Office of Educational Research and Improvement 153.

Weller, H. (1996). Assessing the impact of computer-based learning in science. Journal of Research on Computing in Education, 28(4), 461-486.

Wenglinsky, H. (1998). Does it compute? The relationship between educational technology and student achievement in mathematics. Princeton, NJ: ETS Policy Information Center-Research Division.

Williams, C. (2000). Internet Access in Public Schools and Classrooms: 1994–99, (NCES 2000–086). U.S. Department of Education. Washington, DC: National Center for Education Statistics.

Yocam, K. a. W., F. (1998). Creating an Alternative context for Teacher Development: ACOT's Two-Year Pilot Project. Cupertino, CA, Apple Computer.

# Appendix C – Criteria for EETT Technology Plans

| - PLAN DURATION CRITERION | Page in District office Plan | Example of Adequately Addressed | Example of Not Adequately Addressed |
| --- | --- | --- | --- |
| The plan should guide the county office’s use of education technology for the next three to five years. (For a new plan, can include technology plan development in the first year) | Cover Sheet and Page 3 | The technology plan describes the county offices use of education technology for the next three to five years. (For new plan, description of technology plan development in the first year is acceptable). Specific start and end dates are recorded (7/1/2011 to 6/30/2016). | The plan is less than three years or more than five years in length. Plan duration is 2009-11. |

| - STAKEHOLDERS CRITERION Corresponding EETT Requirement(s): 7 and 11 (Appendix D). | Page in district office Plan | Example of Adequately Addressed | Not Adequately Addressed |
| --- | --- | --- | --- |
| Description of how a variety of stakeholders from within the school county office and the community-at-large participated in the planning process. | 3 | The planning team consisted of representatives who will implement the plan. If a variety of stakeholders did not assist with the development of the plan, a description of why they were not involved is included. | Little evidence is included that shows that the county office actively sought participation from a variety of stakeholders. |

| - CURRICULUM COMPONENT CRITERIA Corresponding EETT Requirement(s): 1, 2, 3, 8, 10, and 12 (Appendix D). | Page in District Plan | Example of Adequately Addressed | Example of Not Adequately Addressed |
| --- | --- | --- | --- |
| - Description of teachers’ and students’ current access to technology tools both during the school day and outside of school hours. | 4-5 | The plan describes the technology access available in the classrooms, library/media centers, or labs for all students and teachers. | The plan explains technology access in terms of a student-to-computer ratio, but does not explain where access is available, who has access, and when various students and teachers can use the technology. |
| - Description of the district’s current use of hardware and software to support teaching and learning. | 5-6 | The plan describes the typical frequency and type of use (technology skills/information literacy/integrated into the curriculum). | The plan cites district policy regarding use of technology, but provides no information about its actual use. |
| - Summary of the district’s curricular goals that are supported by this tech plan. | 6-7 | The plan summarizes the district’s curricular goals that are supported by the plan and referenced in district document(s). | The plan does not summarize district curricular goals. |
| - List of clear goals, measurable objectives, annual benchmarks, and an implementation plan for using technology to improve teaching and learning by supporting the district curricular goals. | 8-11 | The plan delineates clear goals, measurable objectives, annual benchmarks, and a clear implementation plan for using technology to support the district’s curriculum goals and academic content standards to improve learning. | The plan suggests how technology will be used, but is not specific enough to know what action needs to be taken to accomplish the goals. |
| - List of clear goals, measurable objectives, annual benchmarks, and an implementation plan detailing how and when students will acquire the technology skills and information literacy skills needed to succeed in the classroom and the workplace. | 11-12 | The plan delineates clear goal(s), measurable objective(s), annual benchmarks, and an implementation plan detailing how and when students will acquire technology skills and information literacy skills. | The plan suggests how students will acquire technology skills, but is not specific enough to determine what action needs to be taken to accomplish the goals. |

| 3. CURRICULUM COMPONENT CRITERIA (continued) |  | Page in District Plan |  | Example of Adequately Addressed |  | Example of Not Adequately Addressed |
| --- | --- | --- | --- | --- | --- | --- |
| - List of goals and an implementation plan that describe how the district will address the appropriate and ethical use of information technology in the classroom so that students and teachers can distinguish lawful from unlawful uses of copyrighted works, including the following topics: the concept and purpose of both copyright and fair use; distinguishing lawful from unlawful downloading and peer-to-peer file sharing; and avoiding plagiarism. |  | 12-13 |  | The plan describes or delineates clear goals outlining how students and teachers will learn about the concept, purpose, and significance of the ethical use of information technology including copyright, fair use, plagiarism and the implications of illegal file sharing and/or downloading. |  | The plan suggests that students and teachers will be educated in the ethical use of the Internet, but is not specific enough to determine what actions will be taken to accomplish the goals. |
| - List of goals and an implementation plan that describe how the district will address Internet safety, including how students and teachers will be trained to protect online privacy and avoid online predators. |  | 12-13 |  | The plan describes or delineates clear goals outlining how students and teachers will be educated about Internet safety. |  | The plan suggests Internet safety education but is not specific enough to determine what actions will be taken to accomplish the goals of educating students and teachers about internet safety. |
| - Description of or goals about the district policy or practices that ensure equitable technology access for all students. | 14 |  | The plan describes the policy or delineates clear goals and measurable objectives about the policy or practices that ensure equitable technology access for all students. The policy or practices clearly support accomplishing the plan’s goals. |  | The plan does not describe policies or goals that result in equitable technology access for all students. Suggests how technology will be used, but is not specific enough to know what action needs to be taken to accomplish the goals. |  |

| 3. CURRICULUM COMPONENT CRITERIA (continued) | Page in District Plan | Example of Adequately Addressed |  | Example of Not Adequately Addressed |
| --- | --- | --- | --- | --- |
| - List of clear goals, measurable objectives, annual benchmarks, and an implementation plan to use technology to make student record keeping and assessment more efficient and supportive of teachers’ efforts to meet individual student academic needs. | 14-15 | The plan delineates clear goal(s), measurable objective(s), annual benchmarks, and an implementation plan for using technology to support the district’s student record-keeping and assessment efforts. | The plan suggests how technology will be used, but is not specific enough to know what action needs to be taken to accomplish the goals. |  |
| - List of clear goals, measurable objectives, annual benchmarks, and an implementation plan to use technology to improve two-way communication between home and school. | 15-17 | The plan delineates clear goal(s), measurable objective(s), annual benchmarks, and an implementation plan for using technology to improve two-way communication between home and school. | The plan suggests how technology will be used, but is not specific enough to know what action needs to be taken to accomplish the goals. |  |
| - Describe the process that will be used to monitor the Curricular Component (Section 3d-3j) goals, objectives, benchmarks, and planned implementation activities including roles and responsibilities. | 17 | The monitoring process, roles, and responsibilities are described in sufficient detail. | The monitoring process either is absent, or lacks detail regarding procedures, roles, and responsibilities. |  |

| - PROFESSIONAL DEVELOPMENT COMPONENT CRITERIA Corresponding EETT Requirement(s): 5 and 12 (Appendix D). | Page in District Plan | Example of Adequately Addressed | Example of Not Adequately Addressed |
| --- | --- | --- | --- |
| - Summary of the teachers’ and administrators’ current technology proficiency and integration skills and needs for professional development. | 17-19 | The plan provides a clear summary of the teachers’ and administrators’ current technology proficiency and integration skills and needs for professional development. The findings are summarized in the plan by discrete skills that include CTC Standard 9 and 16 proficiencies. | Description of current level of staff expertise is too general or relates only to a limited segment of the district’s teachers and administrators in the focus areas or does not relate to the focus areas, i.e., only the fourth grade teachers when grades four to eight are the focus grade levels. |
| - List of clear goals, measurable objectives, annual benchmarks, and an implementation plan for providing professional development opportunities based on your district needs assessment data (4a) and the Curriculum Component objectives (Sections 3d through 3j) of the plan. | 19-20 | The plan delineates clear goals, measurable objectives, annual benchmarks, and an implementation plan for providing teachers and administrators with sustained, ongoing professional development necessary to reach the Curriculum Component objectives (sections 3d through 3j) of the plan. | The plan speaks only generally of professional development and is not specific enough to ensure that teachers and administrators will have the necessary training to implement the Curriculum Component. |
| - Describe the process that will be used to monitor the Professional Development (Section 4b) goals, objectives, benchmarks, and planned implementation activities including roles and responsibilities. | 24 | The monitoring process, roles, and responsibilities are described in sufficient detail. | The monitoring process either is absent, or lacks detail regarding who is responsible and what is expected. |

| - INFRASTRUCTURE, HARDWARE, TECHNICAL SUPPORT, AND SOFTWARE COMPONENT CRITERIA Corresponding EETT Requirement(s): 6 and 12. | Page in District Plan | Example of Adequately Addressed | Example of Not Adequately Addressed |
| --- | --- | --- | --- |
| - Describe the existing hardware, Internet access, electronic learning resources, and technical support already in the district that will be used to support the Curriculum and Professional Development Components (Sections 3 & 4) of the plan. | 25-28 | The plan clearly summarizes the existing technology hardware, electronic learning resources, networking and telecommunication infrastructure, and technical support to support the implementation of the Curriculum and Professional Development Components. | The inventory of equipment is so general that it is difficult to determine what must be acquired to implement the Curriculum and Professional Development Components. The summary of current technical support is missing or lacks sufficient detail. |
| - Describe the technology hardware, electronic learning resources, networking and telecommunications infrastructure, physical plant modifications, and technical support needed by the district’s teachers, students, and administrators to support the activities in the Curriculum and Professional Development Components of the plan. | 28-29 | The plan provides a clear summary and list of the technology hardware, electronic learning resources, networking and telecommunications infrastructure, physical plant modifications, and technical support the district will need to support the implementation of the district’s Curriculum and Professional Development Components. | The plan includes a description or list of hardware, infrastructure, and other technology necessary to implement the plan, but there doesn’t seem to be any real relationship between the activities in the Curriculum and Professional Development Components and the listed equipment. Future technical support needs have not been addressed or do not relate to the needs of the Curriculum and Professional Development Components. |
| - List of clear annual benchmarks and a timeline for obtaining the hardware, infrastructure, learning resources and technical support required to support the other plan components identified in Section 5b. | 30-32 | The annual benchmarks and timeline are specific and realistic. Teachers and administrators implementing the plan can easily discern what needs to be acquired or repurposed, by whom, and when. | The annual benchmarks and timeline are either absent or so vague that it would be difficult to determine what needs to be acquired or repurposed, by whom, and when. |
| - Describe the process that will be used to monitor Section 5b & the annual benchmarks and timeline of activities including roles and responsibilities. | 32 | The monitoring process, roles, and responsibilities are described in sufficient detail. | The monitoring process either is absent, or lacks detail regarding who is responsible and what is expected. |

| - FUNDING AND BUDGET COMPONENT CRITERIA Corresponding EETT Requirement(s): 7 & 13, (Appendix D) | Page in District Plan | Example of Adequately Addressed | Example of Not Adequately Addressed |
| --- | --- | --- | --- |
| - List established and potential funding sources. | 32 | The plan clearly describes resources that are available or could be obtained to implement the plan. | Resources to implement the plan are not clearly identified or are so general as to be useless. |
| - Estimate annual implementation costs for the term of the plan. | 33 | Cost estimates are reasonable and address the total cost of ownership, including the costs to implement the curricular, professional development, infrastructure, hardware, technical support, and electronic learning resource needs identified in the plan. | Cost estimates are unrealistic, lacking, or are not sufficiently detailed to determine if the total cost of ownership is addressed. |
| - Describe the district’s replacement policy for obsolete equipment. | 35 | Plan recognizes that equipment will need to be replaced and outlines a realistic replacement plan that will support the Curriculum and Professional Development Components. | Replacement policy is either missing or vague. It is not clear that the replacement policy could be implemented. |
| - Describe the process that will be used to monitor Ed Tech funding, implementation costs and new funding opportunities and to adjust budgets as necessary. | 35 | The monitoring process, roles, and responsibilities are described in sufficient detail. | The monitoring process either is absent, or lacks detail regarding who is responsible and what is expected. |

| - MONITORING AND EVALUATION COMPONENT CRITERIA Corresponding EETT Requirement(: 11 (Appendix D). | Page in District Plan | Example of Adequately Addressed | Example of Not Adequately Addressed |
| --- | --- | --- | --- |
| - Describe the process for evaluating the plan’s overall progress and impact on teaching and learning. | 35 | The plan describes the process for evaluation using the goals and benchmarks of each component as the indicators of success. | No provision for an evaluation is included in the plan. How success is determined is not defined. The evaluation is defined, but the process to conduct the evaluation is missing. |
| - Schedule for evaluating the effect of plan implementation. | 36 | Evaluation timeline is specific and realistic. | The evaluation timeline is not included or indicates an expectation of unrealistic results that does not support the continued implementation of the plan. |
| - Describe the process and frequency of communicating evaluation results to tech plan stakeholders. | 36 | The plan describes the process and frequency of communicating evaluation results to tech plan stakeholders. | The plan does not provide a process for using the monitoring and evaluation results to improve the plan and/or disseminate the findings. |

| - EFFECTIVE COLLABORATIVE STRATEGIES WITH ADULT LITERACY PROVIDERS Corresponding EETT Requirement: 11 (Appendix D). | Page in District Plan | Example of Adequately Addressed | Example of Not Adequately Addressed |
| --- | --- | --- | --- |
| - If the district has identified adult literacy providers, describe how the program will be developed in collaboration with them. (If no adult literacy providers are indicated, describe the process used to identify adult literacy providers or potential future outreach efforts.) | 36 | The plan explains how the program will be developed in collaboration with adult literacy providers. Planning included or will include consideration of collaborative strategies and other funding resources to maximize the use of technology. If no adult literacy providers are indicated, the plan describes the process used to identify adult literacy providers or potential future outreach efforts. | There is no evidence that the plan has been, or will be developed in collaboration with adult literacy service providers, to maximize the use of technology. |

| - RESEARCHED-BASED METHODS, STRATEGIES, AND CRITERIA Corresponding EETT Requirement(s): 4 and 9 (Appendix D). | Page in District Plan | Example of Adequately Addressed | Not Adequately Addressed |
| --- | --- | --- | --- |
| - Summarize the relevant research and describe how it supports the plan’s curricular and professional development goals. | 37-39 | The plan describes the relevant research behind the plan’s design for strategies and/or methods selected. | The description of the research behind the plan’s design for strategies and/or methods selected is unclear or missing. |
| - Describe the district’s plans to use technology to extend or supplement the district’s curriculum with rigorous academic courses and curricula, including distance-learning technologies. | 41 | The plan describes the process the district will use to extend or supplement the district’s curriculum with rigorous academic courses and curricula, including distance learning opportunities (particularly in areas that would not otherwise have access to such courses or curricula due to geographical distances or insufficient resources). | There is no plan to use technology to extend or supplement the district’s curriculum offerings. |

| Network Equipment (Note: Most of this equipment is getting replaced during the Fall of 2010 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name | IP Address | Make and Modle | Serial # | Location |
| BESAP1 (access point) | 10.155.212.19 | Cisco AIR-AP1231G-A-K9 | FTX0839J3AT | IDF |
| BHSLAB (access point) | 10.155.212.17 | Cisco AIR-AP1231G-A-K9 | FOC08340D23 | BHS Computer Lab |
| biggsclass1 | 10.155.212.15 | Cisco WS-C2924C-XL | FAA0336H04G |  |
| biggsclass2 | 10.155.212.16 | Cisco WS-C2924C-XL-EN | FAA0336F048 |  |
| biggsclass3 | 10.155.212.20 | Cisco WS-C2924C-XL | FAA0336J04G |  |
| BiggsDistrictMDF |  | Cisco 3550 | CAT0837N0GK | MDF |
| BIGGSELEMIDF1.1 |  | HP 2650xl |  | IDF 1.1 |
| BiggsElemIDF1.2 | 10.155.212.10 | Cisco 3550 | CAT0837N0F2 | IDF 1.2 |
| BiggsElemIDF1.3 | 10.155.212.14 | Cisco 4000 Chassis | FOX03295180 | IDF 1.3 |
| BIGGSELEMIDF1.4 |  | Cisco 2924 | FAA0336L04T | IDF 1.4 |
| BIGGSGATE | 10.155.212.1 | Cisco 3725 | JMX0840L26J | MDF |
| BiggsHighIDF1.2A | 10.155.212.4 | Cisco 3550 | CAT0837N0GH | IDF 1.2 |
| BiggsHighIDF1.2B | 10.155.212.5 | Cisco 3550 | CAT0835Y1MZ | IDF 1.2 |
| BiggsHighIDF1.3 | 10.155.212.6 | Cisco 3550 | CAT0837N0F5 | IDF 1.3 |
| BiggsHighIDF1.4 | 10.155.212.7 | Cisco 3550 | CAT0835X1BH | IDF 1.4 |
| BiggsHighMDFA | 10.155.212.2 | Cisco 4912G | FOX04292092 | MDF |
| BIGGSHIGHMDFB | 10.155.212.3 | Cisco 3550 | CHK0629W0C5 | MDF |
| BIGGSMSMDFA |  | Cisco 3550 | CAT0835Y1PD | MDFA (IDF) |
| BIGGSMSMDFB |  | Cisco 2900 |  | MDFB (IDF) |
| RICHVALEGATE | 10.100.21.1 | Cisco 2621 | SHN030800K7 | MDF |